## KRCF Overall Plan
[11 empty] | 2329.5 | 113.6341 | 29 | 5
[10 empty] | 20.5 |  |  | 145
Project Name | Waterfall Process Model Mapping | Project Execution Phase | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Schedule Duration Total Day's | Duration % orf total | Number of Wipro Eningeers | Total Effort (Person Days) | Total Effor (Person Months)
Avionics_PRJ1_CanSim | Project Initiation and Planning | Project Preparedness Workshop (ppw)
| Requirement Analysis | Requirement Gathering and Prototyping | 31 | 2009-06-30 | 2009-08-07 |  | 28.8372
| Architecture and Design | Design | 31.5 | 2009-08-10 | 2009-09-21 |  | 29.3023
| CUT/Implementation | Coding, Reviews and Unit Testing | 27 | 2009-09-22 | 2009-10-28 |  | 25.1163
| System Integration and Testing | Integration and System Testing | 11 | 2009-10-29 | 2009-11-11 |  | 10.2326
| NA | White Paper | 7 | 2009-11-12 | 2009-11-17 |  | 6.5116
[6 empty] | 107.5 |  | 2 | 215 | 10.4878
Avionics_PRJ2_ARINC615 | Project Initiation and Planning | Project Preparedness Workshop (ppw)
| Requirement Analysis | Requirement Gathering and Prototyping | 31 | 2009-06-30 | 2009-08-07 |  | 28.8372
| Architecture and Design | Design | 31.5 | 2009-08-10 | 2009-09-21 |  | 29.3023
| CUT/Implementation | Coding, Reviews and Unit Testing | 27 | 2009-09-22 | 2009-10-28 |  | 25.1163
| System Integration and Testing | Integration and System Testing | 11 | 2009-10-29 | 2009-11-11 |  | 10.2326
| NA | White Paper | 7 | 2009-11-12 | 2009-11-17 |  | 6.5116
[6 empty] | 107.5 |  | 3 | 322.5 | 15.7317
Avionics_PRJ3_IPV4V6 | Project Initiation and Planning | Project Preparedness Workshop (ppw)
| Requirement Analysis | Requirement Gathering and Prototyping | 30 | 2009-06-30 | 2009-08-07 |  | 28.0374
| Architecture and Design | Design | 31 | 2009-08-10 | 2009-09-22 |  | 28.972
| CUT/Implementation | Coding, Reviews and Unit Testing | 27 | 2009-09-22 | 2009-10-29 |  | 25.2336
| System Integration and Testing | Integration and System Testing | 13 | 2009-10-29 | 2009-11-17 |  | 12.1495
| NA | White Paper | 6 | 2009-11-17 | 2009-11-25 |  | 5.6075
[6 empty] | 107 |  | 2 | 214 | 10.439
Multimedia_VideoAnalytics | Project Initiation and Planning | Project Preparedness Workshop (ppw) | 4 | 2009-06-25 | 2009-06-30 |  | 3.5714
| Requirement Analysis | Requirement Gathering and Prototyping | 24 | 2009-07-01 | 2009-08-03 |  | 21.4286
| Architecture and Design | Design | 32 | 2009-08-04 | 2009-09-16 |  | 28.5714
| CUT/Implementation | Coding, Reviews and Unit Testing | 25 | 2009-09-17 | 2009-10-21 |  | 22.3214
| System Integration and Testing | Integration and System Testing | 15 | 2009-10-22 | 2009-11-11 |  | 13.3929
| NA | White Paper | 12 | 2009-11-12 | 2009-11-27 |  | 10.7143
[6 empty] | 112 |  | 3 | 336 | 16.3902
Multimedia_ALCFlute | Project Initiation and Planning | Project Preparedness Workshop (ppw) | 3 | 2009-06-26 | 2009-06-30 |  | 3.75
Iteration 1 | Requirement Analysis | Requirement Gathering and Prototyping | 16 | 2009-07-01 | 2009-07-22 |  | 20
| Architecture and Design | Design | 15 | 2009-07-23 | 2009-08-12 |  | 18.75
| CUT/Implementation | Coding, Reviews and Unit Testing | 15 | 2009-08-13 | 2009-09-03 |  | 18.75
| System Integration and Testing | Integration and System Testing | 21 | 2009-09-04 | 2009-10-02 |  | 26.25
| NA | White Paper | 10 | 2009-08-25 | 2009-09-08 |  | 12.5
[6 empty] | 80 |  | 3 | 240 | 11.7073
Multimedia_ALCFlute | Project Initiation and Planning | Project Preparedness Workshop (ppw) | 1 | 2009-10-05 | 2009-10-05 |  | 3.3333
Iteration 2 | Requirement Analysis | Requirement Gathering and Prototyping | 7 | 2009-10-06 | 2009-10-14 |  | 23.3333
| Architecture and Design | Design | 10 | 2009-10-15 | 2009-10-28 |  | 33.3333
| CUT/Implementation | Coding, Reviews and Unit Testing | 8 | 2009-10-29 | 2009-11-09 |  | 26.6667
| System Integration and Testing | Integration and System Testing | 4 | 2009-11-09 | 2009-11-13 |  | 13.3333
| NA | White Paper |  |  |  | 30 |  | 3 | 90 | 4.3902
DBMS_PRJ1_ShortCut | Project Initiation and Planning | Project Preparedness Workshop (ppw) | 15 | 2009-06-22 | 2009-06-30 |  | 12.605
| Requirement Analysis | Requirement Gathering and Prototyping | 31 | 2009-07-08 | 2009-08-11 |  | 26.0504
| Architecture and Design | Design | 33 | 2009-08-12 | 2009-09-30 |  | 27.7311
| CUT/Implementation | Coding, Reviews and Unit Testing | 25 | 2009-10-01 | 2009-03-07 |  | 21.0084
| System Integration and Testing | Integration and System Testing | 10 | 2009-11-03 | 2009-11-14 |  | 8.4034
| NA | White Paper | 5 | 2009-11-15 | 2009-11-21 |  | 4.2017
[6 empty] | 119 |  | 1 | 119 | 5.8049
DBMS_PRJ2_DT | Project Initiation and Planning | Project Preparedness Workshop (ppw) | 15 | 2009-06-22 | 2009-06-30 |  | 12.605
| Requirement Analysis | Requirement Gathering and Prototyping | 31 | 2009-07-08 | 2009-08-11 |  | 26.0504
| Architecture and Design | Design | 33 | 2009-08-12 | 2009-09-30 |  | 27.7311
| CUT/Implementation | Coding, Reviews and Unit Testing | 25 | 2009-10-01 | 2009-03-07 |  | 21.0084
| System Integration and Testing | Integration and System Testing | 10 | 2009-11-03 | 2009-11-14 |  | 8.4034
| NA | White Paper | 5 | 2009-11-15 | 2009-11-21 |  | 4.2017
[6 empty] | 119 |  | 2 | 238 | 11.6098
DBMS_PRJ3_GRMTST | Project Initiation and Planning | Project Preparedness Workshop (ppw) | 15 | 2009-06-22 | 2009-06-30 |  | 13.6364
| Requirement Analysis | Requirement Gathering and Prototyping | 9 | 2009-07-08 | 2009-07-21 |  | 8.1818
| Architecture and Design | Design | 23 | 2009-07-22 | 2009-08-21 |  | 20.9091
| CUT/Implementation | Coding, Reviews and Unit Testing | 38 | 25/08/2009 | 16-10-2009 |  | 34.5455
| System Integration and Testing | Integration and System Testing | 20 | 2009-10-20 | 2009-11-13 |  | 18.1818
| NA | White Paper | 5 | 2009-11-15 | 2009-11-21 |  | 4.5455
[6 empty] | 110 |  | 2 | 220 | 10.7317
CloudComputing | Project Initiation and Planning | Project Preparedness Workshop (ppw) | 16 | 2009-06-25 | 2009-07-16 |  | 14.4144
| Requirement Analysis | Requirement Gathering and Prototyping | 16 | 2009-07-17 | 2009-08-07 |  | 14.4144
| Architecture and Design | Design | 20 | 2009-08-10 | 2009-09-07 |  | 18.018
| CUT/Implementation | Coding, Reviews and Unit Testing | 24 | 2009-09-08 | 2009-10-09 |  | 21.6216
| System Integration and Testing | Integration and System Testing | 25 | 2009-10-12 | 2009-11-13 |  | 22.5225
| NA | White Paper | 10 | 2009-08-25 | 2009-09-08 |  | 9.009
[6 empty] | 111 |  | 2 | 222 | 10.8293
HPC | Project Initiation and Planning | Project Preparedness Workshop (ppw)
| Requirement Analysis | Requirement Gathering and Prototyping | 20 | 2009-07-08 | 2009-08-04 |  | 17.6991
| Architecture and Design | Design | 20 | 2009-08-05 | 2009-09-01 |  | 17.6991
| CUT/Implementation | Coding, Reviews and Unit Testing | 49 | 2009-09-02 | 2009-11-09 |  | 43.3628
| System Integration and Testing | Integration and System Testing | 14 | 2009-11-10 | 2009-11-20 |  | 12.3894
| NA | White Paper | 10 | 2009-09-10 | 2009-10-15 |  | 8.8496
[6 empty] | 113 |  | 1 | 113 | 5.5122
Note on E4: ganesh: Overall Days for this phase
Note on F4: ganesh: Start date of this phase
Note on G4: ganesh: End Date of this phase
Note on E11: ganesh: Overall Days for this phase
Note on F11: ganesh: Start date of this phase
Note on G11: ganesh: End Date of this phase
Note on E18: ganesh: Overall Days for this phase
Note on F18: ganesh: Start date of this phase
Note on G18: ganesh: End Date of this phase
Note on E25: ganesh: Overall Days for this phase
Note on F25: ganesh: Start date of this phase
Note on E67: ganesh: Overall Days for this phase
Note on F67: ganesh: Start date of this phase
Note on E74: ganesh: Overall Days for this phase
Note on F74: ganesh: Start date of this phase
Note on G74: ganesh: End Date of this phase
Note on E46: ganesh: Overall Days for this phase
Note on F46: ganesh: Start date of this phase
Note on G46: ganesh: End Date of this phase
Note on G60: ganesh: End Date of this phase
Note on F60: ganesh: Start date of this phase
Note on E60: ganesh: Overall Days for this phase
Note on G53: ganesh: End Date of this phase
Note on F53: ganesh: Start date of this phase
Note on E53: ganesh: Overall Days for this phase
Note on E39: ganesh: Overall Days for this phase
Note on F39: ganesh: Start date of this phase
Note on G25: ganesh: Start date of this phase
Note on G67: ganesh: Start date of this phase
Note on G39: ganesh: Start date of this phase
Note on E32: ganesh: Overall Days for this phase
Note on F32: ganesh: Start date of this phase
Note on G32: ganesh: End Date of this phase

## ProjectOwnerMapping
# | Project | Mapping
1 | Avionics_PRJ1_CanSim | Umesh Singh
2 | Avionics_PRJ2_ARINC615 | Umesh Singh
3 | Avionics_PRJ3_IPV4V6 | Srirama Sharma
4 | MultimediaVideoAnalytics | Arunkumar Singh
5 | MultimediaALCFlute | Santosh Joshi
6 | DBMS_PRJ1_ShortCut | Harish N
7 | DBMS_PRJ2_DT | Harish N
8 | DBMS_PRJ3_GRMTest | Harish N
9 | Cloud Computing | Santosh Joshi
10 | HPC | Amlan
| Important Milestones | Date
| Project Preparedness Workshop | 15-Jun-09 to 26-Jun-09
| Project Start Date | 2009-06-29
| Project End Date | 2009-12-02
| Internal Audit - 1 | 2009-08-20
| Internal Audit - 1 | 2009-10-15
| Internal Audit - 1 | 2009-11-25
| PDMR/PMR | 29th of every month

## Template
Waterfall Process Model Mapping | Project Execution Phase | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Activities | Applicable (Yes/No) | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Wipro Engineers Effort (PHRS) | Wipro Engineers Effort (Pdays)
Project Initiation and Planning | Project Preparedness Workshop (ppw)
Finalization & White paper generation of project titles
Briefing of project titles
Micro Project definition
Project Team Formation
Project plan - work book preparation
Kick-off Meeting for individual projects
Requirement Analysis | Requirement Gathering and Prototyping
LAM - Requirement Analysis
Identification of Requirement Gathering Technique
Identification of Functional and Non Functional Requirements
Identification of Performance Requirements of System
Inputs and Outputs to system
User Interface (if any) and Data Requirements
Internal External Interface Identification
Environmental Constraints
Requirement Related to Safety, security, and reliability aspects
Saturatory and Regulatory Requirements (If any)
System/Business Use case generation
Identification and prioritization of requirements
Assigning Unique ID to each requirement
Preparation of Requirement Specification
Preparation of Requirement Traceability Sheet
Requirements Review
Bugzilla - Review defect update
Review comment analysis with team
Prototyping Critical Requirements
Configuration Audit
KRCF - Engineers Performance Appraisal
Release - Requirement Analysis Phase
Architecture and Design | Design
LAM - Architecture and Design
Prepare Overall Architecture, Design Pattern
Modular Breakdown and interface diagram
Identification and selection of appropriate design Methodologies (e.g. structure module, OOD, Design patterns etc.)
Design Alternative consideration
High Level Design (HLD) - Preparation
Critical Data structures
HLD Review
Bugzilla - Review Defect update (HLD)
Low Level Design (LLD) Pseudo code development
LLD Review
Bugzilla - Review Defect update (LLD)
SCM set-up for build version and release
Test Design and test cases generation
Update Bi-directional Traceability
Review Comment Analysis with team
Configuration Audit
KRCF - Engineers Performance Appraisal
Release - Architecture and Design
CUT/Implementation | Coding, Reviews and Unit Testing
LAM - CUT /Implementation
Build Setup and Build procedure documentation/guidelines
Identification of inter module dependencies
Development of the code using appropriate method - structured programming, Object Oriented Programming, Design Pattern
Coding as per guidelines
Static Analysis of Code using - WiproStyle/Jtest/C++ Test/Lints/Other Tools
Review of Critical section of Code
Bugzilla - Review comments update
Preparation of Unit Test plan and test cases
Unit Testing of components using open source testing and debugging tools
Documentation and Packaging
Update Bidirectional Traceability Matrix
Configuration Audit
Review comment analysis with team
KRCF - Engineers Performance Appraisal
Release - Cut/Implementation
System Integration and Testing | Integration and System Testing
LAM - System testing and Testing
Prepare System Test plan and test cases
Modular testing
Modular interface integration
Build and Release
Configuration Audit
System testing: Execution of test cases as per test plan in 2 cycles with bug fixing
Perform testing for - Functional testing, Performance testing , Reliability testing, Usability Testing, Load Testing, Volume and Stress Testing
Update test result and Traceability sheet
Test Result Analysis with Team
Project Presentation to KRCF & Wipro
KRCF - Engineers Performance Appraisal
NA | White Paper
Preparation of While paper abstract and review
Study of the identified topics for white paper
Preparation White paper abstract
Final review of the White paper
Presentation of KRCF team
Note on D4: ganesh: Overall Days for this phase
Note on E4: ganesh: Start date of this phase
Note on F4: ganesh: End Date of this phase

## Avionics_PRJ1_CanSim
Waterfall Process Model Mapping | Project Execution Phase | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Activities | Applicable (Yes/No) | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Wipro Engineers Effort (PHRS) | Wipro Engineers Effort (Pdays)
Project Initiation and Planning | Project Preparedness Workshop (ppw)
Finalization & White paper generation of project titles
Briefing of project titles
Micro Project definition
Project Team Formation
Project plan - work book preparation
Kick-off Meeting for individual projects
Requirement Analysis | Requirement Gathering and Prototyping | 31 | 2009-06-30 | 2009-08-07
[5 empty] | LAM - Requirement Analysis | y | 1 | 2009-06-30 | 2009-06-30 |  | 0.5
[5 empty] | Identification of Requirement Gathering Technique | y | 1 | 2009-06-30 | 2009-06-30 |  | 0.5
[5 empty] | Identification of Functional and Non Functional Requirements | y | 4 | 2009-07-01 | 2009-07-06 |  | 2
[5 empty] | Identification of Performance Requirements of System | y | 1 | 2009-07-07 | 2009-07-07 |  | 0.5
[5 empty] | Inputs and Outputs to system | y | 2 | 2009-07-08 | 2009-07-09 |  | 1
[5 empty] | User Interface (if any) and Data Requirements | y | 1 | 2009-07-10 | 2009-07-10 |  | 0.5
[5 empty] | Internal External Interface Identification | y | 1 | 2009-07-13 | 2009-07-13 |  | 0.5
[5 empty] | Environmental Constraints | y | 1 | 2009-07-14 | 2009-07-14 |  | 0.5
[5 empty] | Requirement Related to Safety, security, and reliability aspects | y | 1 | 2009-07-15 | 2009-07-15 |  | 0.5
[5 empty] | Saturatory and Regulatory Requirements (If any) | y | 1 | 2009-07-16 | 2009-07-16 |  | 0.5
[5 empty] | System/Business Use case generation | y | 4 | 2009-07-17 | 2009-07-22 |  | 2
[5 empty] | Identification and prioritization of requirements | y | 2 | 2009-07-23 | 2009-07-24 |  | 1
[5 empty] | Assigning Unique ID to each requirement | y | 1 | 2009-07-27 | 2009-07-27 |  | 0.5
[5 empty] | Preparation of Requirement Specification | y | 4 | 2009-07-27 | 2009-07-30 |  | 2
[5 empty] | Preparation of Requirement Traceability Sheet | y | 1 | 2009-07-31 | 2009-07-31 |  | 0.5
[5 empty] | Requirements Review | y | 1 | 2009-08-03 | 2009-08-03 |  | 0.5
[5 empty] | Bugzilla - Review defect update | y | 0.5 | 2009-08-04 | 2009-08-04 |  | 0.5
[5 empty] | Review comment analysis with team | y | 0.5 | 2009-08-04 | 2009-08-04 |  | 0.5
[5 empty] | Prototyping Critical Requirements | y | 1 | 2009-08-05 | 2009-08-05 |  | 0.5
[5 empty] | Configuration Audit | y | 0.5 | 2009-08-06 | 2009-08-06 |  | 0.5
[5 empty] | KRCF - Engineers Performance Appraisal | y | 0.5 | 2009-08-06 | 2009-08-06 |  | 0.5
[5 empty] | Release - Requirement Analysis Phase | y | 1 | 2009-08-07 | 2009-08-07 |  | 0.5
Architecture and Design | Design | 31.5 | 2009-08-10 | 2009-09-21
[5 empty] | LAM - Architecture and Design | y | 1 | 2009-08-10 | 2009-08-10 |  | 0.5
[5 empty] | Prepare Overall Architecture, Design Pattern | y | 4 | 2009-08-11 | 2009-08-14 |  | 2
[5 empty] | Modular Breakdown and interface diagram | y | 2 | 2009-08-17 | 2009-08-18 |  | 1
[5 empty] | Identification and selection of appropriate design Methodologies (e.g. structure module, OOD, Design patterns etc.) | y |  | Covered in Design Prep
[5 empty] | Design Alternative consideration | n |  | Covered in Design Prep
[5 empty] | High Level Design (HLD) - Preparation | y | 4 | 2009-08-19 | 2009-08-24 |  | 2
[5 empty] | Critical Data structures | n |  | Covered in pseudo code development
[5 empty] | HLD Review | y | 1 | 2009-08-25 | 2009-08-25 |  | 0.5
[5 empty] | Bugzilla - Review Defect update (HLD) | y | 0.5 | 2009-08-26 | 2009-08-26 |  | 0.5
[5 empty] | Low Level Design (LLD) Pseudo code development | y | 7 | 2009-08-26 | 2009-09-03 |  | 3
[5 empty] | LLD Review | y | 2 | 2009-09-04 | 2009-09-07 |  | 1
[5 empty] | Bugzilla - Review Defect update (LLD) | y | 1 | 2009-09-08 | 2009-09-08 |  | 0.5
[5 empty] | SCM set-up for build version and release | y | 1 | 2009-09-09 | 2009-09-09 |  | 0.5
[5 empty] | Test Design and test cases generation | y | 4 | 2009-09-10 | 2009-09-15 |  | 2
[5 empty] | Update Bi-directional Traceability | y | 1 | 2009-09-16 | 2009-09-16 |  | 0.5
[5 empty] | Review Comment Analysis with team | y | 1 | 2009-09-17 | 2009-09-17 |  | 0.5
[5 empty] | Configuration Audit | y | 0.5 | 2009-09-18 | 2009-09-18 |  | 0.5
[5 empty] | KRCF - Engineers Performance Appraisal | y | 0.5 | 2009-09-18 | 2009-09-18 |  | 0.5
[5 empty] | Release - Architecture and Design | y | 1 | 2009-09-21 | 2009-09-21 |  | 0.5
CUT/Implementation | Coding, Reviews and Unit Testing | 27 | 2009-09-22 | 2009-10-28
[5 empty] | LAM - CUT /Implementation | y | 1 | 2009-09-22 | 2009-09-22 |  | 0.5
[5 empty] | Build Setup and Build procedure documentation/guidelines | y | 1 | 2009-09-23 | 2009-09-23 |  | 0.5
[5 empty] | Identification of inter module dependencies | y | 1 | 2009-09-24 | 2009-09-24 |  | 0.5
[5 empty] | Development of the code using appropriate method - structured programming, Object Oriented Programming, Design Pattern | y | 11 | 2009-09-25 | 2009-10-09 |  | 5
[5 empty] | Coding as per guidelines | y | 11 | 2009-09-25 | 2009-10-09 |  | 5
[5 empty] | Static Analysis of Code using - WiproStyle/Jtest/C++ Test/Lints/Other Tools | y | 2 | 2009-10-12 | 2009-10-13 |  | 1
[5 empty] | Review of Critical section of Code | n |  | Done during Coding
[5 empty] | Bugzilla - Review comments update | y | 1 | 2009-10-14 | 2009-10-14 |  | 0.5
[5 empty] | Preparation of Unit Test plan and test cases | y | 2 | 2009-10-15 | 2009-10-16 |  | 1
[5 empty] | Unit Testing of components using open source testing and debugging tools | y | 3 | 2009-10-19 | 2009-10-21 |  | 2
[5 empty] | Documentation and Packaging | y | 4 | 2009-10-22 | 2009-10-27 |  | 2
[5 empty] | Update Bidirectional Traceability Matrix | y | 4 | 2009-10-22 | 2009-10-27 |  | 2
[5 empty] | Configuration Audit | y | 4 | 2009-10-22 | 2009-10-27 |  | 2
[5 empty] | Review comment analysis with team | y | 4 | 2009-10-22 | 2009-10-27 |  | 2
[5 empty] | KRCF - Engineers Performance Appraisal | y | 4 | 2009-10-22 | 2009-10-27 |  | 2
[5 empty] | Release - Cut/Implementation | y | 1 | 2009-10-28 | 2009-10-28 |  | 0.5
System Integration and Testing | Integration and System Testing | 11 | 2009-10-29 | 2009-11-11
[5 empty] | LAM - System testing and Testing | y | 1 | 2009-10-29 | 2009-10-29 |  | 0.5
[5 empty] | Prepare System Test plan and test cases | y | 3 | 2009-10-30 | 2009-11-03 |  | 2
[5 empty] | Modular testing | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | Modular interface integration | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | Build and Release | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | Configuration Audit | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | System testing: Execution of test cases as per test plan in 2 cycles with bug fixing | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | Perform testing for - Functional testing, Performance testing , Reliability testing, Usability Testing, Load Testing, Volume and Stress Testing | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | Update test result and Traceability sheet | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | Test Result Analysis with Team | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | Project Presentation to KRCF & Wipro | y | 1 | 2009-11-11 | 2009-11-11 |  | 0.5
[5 empty] | KRCF - Engineers Performance Appraisal | y
NA | White Paper | 7 | 2009-11-12 | 2009-11-17
[5 empty] | Preparation of While paper abstract and review | y | 1 | 2009-11-12 | 2009-11-12 |  | 0.5
[5 empty] | Study of the identified topics for white paper | y | 2 | 2009-11-12 | 2009-11-13 |  | 1
[5 empty] | Preparation White paper abstract | y | 2 | 2009-11-13 | 2009-11-16 |  | 1
[5 empty] | Final review of the White paper | y | 1 | 2009-11-16 | 2009-11-16 |  | 0.5
[5 empty] | Presentation of KRCF team | y | 1 | 2009-11-17 | 2009-11-17 |  | 0.5
Formulas:
Start Date (DD-MON-YY) = [Start Date (DD-MON-YY), row below]
Note on D4: ganesh: Overall Days for this phase
Note on E4: ganesh: Start date of this phase
Note on F4: ganesh: End Date of this phase

## Avionics_PRJ2_ARINC615
Waterfall Process Model Mapping | Project Execution Phase | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Activities | Applicable (Yes/No) | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Wipro Engineers Effort (PHRS) | Wipro Engineers Effort (Pdays)
Project Initiation and Planning | Project Preparedness Workshop (ppw)
Finalization & White paper generation of project titles
Briefing of project titles
Micro Project definition
Project Team Formation
Project plan - work book preparation
Kick-off Meeting for individual projects
Requirement Analysis | Requirement Gathering and Prototyping | 31 | 2009-06-30 | 2009-08-07
[5 empty] | LAM - Requirement Analysis | y | 1 | 2009-06-30 | 2009-06-30 |  | 0.5
[5 empty] | Identification of Requirement Gathering Technique | y | 1 | 2009-06-30 | 2009-06-30 |  | 0.5
[5 empty] | Identification of Functional and Non Functional Requirements | y | 4 | 2009-07-01 | 2009-07-06 |  | 2
[5 empty] | Identification of Performance Requirements of System | y | 1 | 2009-07-07 | 2009-07-07 |  | 0.5
[5 empty] | Inputs and Outputs to system | y | 2 | 2009-07-08 | 2009-07-09 |  | 1
[5 empty] | User Interface (if any) and Data Requirements | y | 1 | 2009-07-10 | 2009-07-10 |  | 0.5
[5 empty] | Internal External Interface Identification | y | 1 | 2009-07-13 | 2009-07-13 |  | 0.5
[5 empty] | Environmental Constraints | y | 1 | 2009-07-14 | 2009-07-14 |  | 0.5
[5 empty] | Requirement Related to Safety, security, and reliability aspects | y | 1 | 2009-07-15 | 2009-07-15 |  | 0.5
[5 empty] | Saturatory and Regulatory Requirements (If any) | y | 1 | 2009-07-16 | 2009-07-16 |  | 0.5
[5 empty] | System/Business Use case generation | y | 4 | 2009-07-17 | 2009-07-22 |  | 2
[5 empty] | Identification and prioritization of requirements | y | 2 | 2009-07-23 | 2009-07-24 |  | 1
[5 empty] | Assigning Unique ID to each requirement | y | 1 | 2009-07-27 | 2009-07-27 |  | 0.5
[5 empty] | Preparation of Requirement Specification | y | 4 | 2009-07-27 | 2009-07-30 |  | 2
[5 empty] | Preparation of Requirement Traceability Sheet | y | 1 | 2009-07-31 | 2009-07-31 |  | 0.5
[5 empty] | Requirements Review | y | 1 | 2009-08-03 | 2009-08-03 |  | 0.5
[5 empty] | Bugzilla - Review defect update | y | 0.5 | 2009-08-04 | 2009-08-04 |  | 0.5
[5 empty] | Review comment analysis with team | y | 0.5 | 2009-08-04 | 2009-08-04 |  | 0.5
[5 empty] | Prototyping Critical Requirements | y | 1 | 2009-08-05 | 2009-08-05 |  | 0.5
[5 empty] | Configuration Audit | y | 0.5 | 2009-08-06 | 2009-08-06 |  | 0.5
[5 empty] | KRCF - Engineers Performance Appraisal | y | 0.5 | 2009-08-06 | 2009-08-06 |  | 0.5
[5 empty] | Release - Requirement Analysis Phase | y | 1 | 2009-08-07 | 2009-08-07 |  | 0.5
Architecture and Design | Design | 31.5 | 2009-08-10 | 2009-09-21
[5 empty] | LAM - Architecture and Design | y | 1 | 2009-08-10 | 2009-08-10 |  | 0.5
[5 empty] | Prepare Overall Architecture, Design Pattern | y | 4 | 2009-08-11 | 2009-08-14 |  | 2
[5 empty] | Modular Breakdown and interface diagram | y | 2 | 2009-08-17 | 2009-08-18 |  | 1
[5 empty] | Identification and selection of appropriate design Methodologies (e.g. structure module, OOD, Design patterns etc.) | y |  | Covered in Design Prep
[5 empty] | Design Alternative consideration | n |  | Covered in Design Prep
[5 empty] | High Level Design (HLD) - Preparation | y | 4 | 2009-08-19 | 2009-08-24 |  | 2
[5 empty] | Critical Data structures | n |  | Covered in pseudo code development
[5 empty] | HLD Review | y | 1 | 2009-08-25 | 2009-08-25 |  | 0.5
[5 empty] | Bugzilla - Review Defect update (HLD) | y | 0.5 | 2009-08-26 | 2009-08-26 |  | 0.5
[5 empty] | Low Level Design (LLD) Pseudo code development | y | 7 | 2009-08-26 | 2009-09-03 |  | 3
[5 empty] | LLD Review | y | 2 | 2009-09-04 | 2009-09-07 |  | 1
[5 empty] | Bugzilla - Review Defect update (LLD) | y | 1 | 2009-09-08 | 2009-09-08 |  | 0.5
[5 empty] | SCM set-up for build version and release | y | 1 | 2009-09-09 | 2009-09-09 |  | 0.5
[5 empty] | Test Design and test cases generation | y | 4 | 2009-09-10 | 2009-09-15 |  | 2
[5 empty] | Update Bi-directional Traceability | y | 1 | 2009-09-16 | 2009-09-16 |  | 0.5
[5 empty] | Review Comment Analysis with team | y | 1 | 2009-09-17 | 2009-09-17 |  | 0.5
[5 empty] | Configuration Audit | y | 0.5 | 2009-09-18 | 2009-09-18 |  | 0.5
[5 empty] | KRCF - Engineers Performance Appraisal | y | 0.5 | 2009-09-18 | 2009-09-18 |  | 0.5
[5 empty] | Release - Architecture and Design | y | 1 | 2009-09-21 | 2009-09-21 |  | 0.5
CUT/Implementation | Coding, Reviews and Unit Testing | 27 | 2009-09-22 | 2009-10-28
[5 empty] | LAM - CUT /Implementation | y | 1 | 2009-09-22 | 2009-09-22 |  | 0.5
[5 empty] | Build Setup and Build procedure documentation/guidelines | y | 1 | 2009-09-23 | 2009-09-23 |  | 0.5
[5 empty] | Identification of inter module dependencies | y | 1 | 2009-09-24 | 2009-09-24 |  | 0.5
[5 empty] | Development of the code using appropriate method - structured programming, Object Oriented Programming, Design Pattern | y | 11 | 2009-09-25 | 2009-10-09 |  | 5
[5 empty] | Coding as per guidelines | y | 11 | 2009-09-25 | 2009-10-09 |  | 5
[5 empty] | Static Analysis of Code using - WiproStyle/Jtest/C++ Test/Lints/Other Tools | y | 2 | 2009-10-12 | 2009-10-13 |  | 1
[5 empty] | Review of Critical section of Code | n |  | Done during Coding
[5 empty] | Bugzilla - Review comments update | y | 1 | 2009-10-14 | 2009-10-14 |  | 0.5
[5 empty] | Preparation of Unit Test plan and test cases | y | 2 | 2009-10-15 | 2009-10-16 |  | 1
[5 empty] | Unit Testing of components using open source testing and debugging tools | y | 3 | 2009-10-19 | 2009-10-21 |  | 2
[5 empty] | Documentation and Packaging | y | 4 | 2009-10-22 | 2009-10-27 |  | 2
[5 empty] | Update Bidirectional Traceability Matrix | y | 4 | 2009-10-22 | 2009-10-27 |  | 2
[5 empty] | Configuration Audit | y | 4 | 2009-10-22 | 2009-10-27 |  | 2
[5 empty] | Review comment analysis with team | y | 4 | 2009-10-22 | 2009-10-27 |  | 2
[5 empty] | KRCF - Engineers Performance Appraisal | y | 4 | 2009-10-22 | 2009-10-27 |  | 2
[5 empty] | Release - Cut/Implementation | y | 1 | 2009-10-28 | 2009-10-28 |  | 0.5
System Integration and Testing | Integration and System Testing | 11 | 2009-10-29 | 2009-11-11
[5 empty] | LAM - System testing and Testing | y | 1 | 2009-10-29 | 2009-10-29 |  | 0.5
[5 empty] | Prepare System Test plan and test cases | y | 3 | 2009-10-30 | 2009-11-03 |  | 2
[5 empty] | Modular testing | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | Modular interface integration | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | Build and Release | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | Configuration Audit | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | System testing: Execution of test cases as per test plan in 2 cycles with bug fixing | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | Perform testing for - Functional testing, Performance testing , Reliability testing, Usability Testing, Load Testing, Volume and Stress Testing | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | Update test result and Traceability sheet | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | Test Result Analysis with Team | y | 6 | 2009-11-03 | 2009-11-10 |  | 3
[5 empty] | Project Presentation to KRCF & Wipro | y | 1 | 2009-11-11 | 2009-11-11 |  | 0.5
[5 empty] | KRCF - Engineers Performance Appraisal | y
NA | White Paper | 7 | 2009-11-12 | 2009-11-17
[5 empty] | Preparation of While paper abstract and review | y | 1 | 2009-11-12 | 2009-11-12 |  | 0.5
[5 empty] | Study of the identified topics for white paper | y | 2 | 2009-11-12 | 2009-11-13 |  | 1
[5 empty] | Preparation White paper abstract | y | 2 | 2009-11-13 | 2009-11-16 |  | 1
[5 empty] | Final review of the White paper | y | 1 | 2009-11-16 | 2009-11-16 |  | 0.5
[5 empty] | Presentation of KRCF team | y | 1 | 2009-11-17 | 2009-11-17 |  | 0.5
Formulas:
Start Date (DD-MON-YY) = [Start Date (DD-MON-YY), row below]
Note on D4: ganesh: Overall Days for this phase
Note on E4: ganesh: Start date of this phase
Note on F4: ganesh: End Date of this phase

## Avionics_PRJ3_IPV4V6
Waterfall Process Model Mapping | Project Execution Phase | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Activities | Applicable (Yes/No) | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Wipro Engineers Effort (PHRS) | Wipro Engineers Effort (Pdays)
Project Initiation and Planning | Project Preparedness Workshop (ppw) |  |  | 2009-06-30
Finalization & White paper generation of project titles
[5 empty] | Briefing of project titles | Yes
[5 empty] | Micro Project definition | Yes
[5 empty] | Project Team Formation | Yes
[5 empty] | Project plan - work book preparation | Yes
[5 empty] | Kick-off Meeting for individual projects | Yes | 1 | 2009-06-29 | 2009-06-30
Requirement Analysis | Requirement Gathering and Prototyping | 30 | 2009-06-30 | 2009-08-07
[5 empty] | LAM - Requirement Analysis | Yes | 1 | 2009-06-30 | 2009-07-01
[5 empty] | Identification of Requirement Gathering Technique | Yes | 1 | 2009-07-01 | 2009-07-02
[5 empty] | Identification of Functional and Non Functional Requirements | Yes | 4 | 2009-07-02 | 2009-07-08
Identification of Performance Requirements of System
[5 empty] | Inputs and Outputs to system | Yes | 2 | 2009-07-08 | 2009-07-10
[5 empty] | User Interface (if any) and Data Requirements | Yes | 2
Internal External Interface Identification
[5 empty] | Environmental Constraints | Yes | 3 | 2009-07-10 | 2009-07-15
[5 empty] | Requirement Related to Safety, security, and reliability aspects | Yes | 1 | 2009-07-15 | 2009-07-16
Saturatory and Regulatory Requirements (If any)
System/Business Use case generation
[5 empty] | Identification and prioritization of requirements | Yes | 3 | 2009-07-16 | 2009-07-21
[5 empty] | Assigning Unique ID to each requirement | Yes | 1 | 2009-07-21 | 2009-07-22
[5 empty] | Preparation of Requirement Specification | Yes | 3 | 2009-07-22 | 2009-07-27
[5 empty] | Preparation of Requirement Traceability Sheet | Yes | 1 | 2009-07-27 | 2009-07-28
[5 empty] | Requirements Review | Yes | 2 | 2009-07-28 | 2009-07-30
Bugzilla - Review defect update
[5 empty] | Review comment analysis with team | Yes | 1 | 2009-07-30 | 2009-07-31
[5 empty] | Prototyping Critical Requirements | Yes | 1 | 2009-07-31 | 2009-08-03
[5 empty] | Configuration Audit | Yes | 2 | 2009-08-03 | 2009-08-05
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 1 | 2009-08-05 | 2009-08-06
[5 empty] | Release - Requirement Analysis Phase | Yes | 1 | 2009-08-06 | 2009-08-07
Architecture and Design | Design | 31 | 2009-08-10 | 2009-09-22
[5 empty] | LAM - Architecture and Design | Yes | 1 | 2009-08-10 | 2009-08-11
[5 empty] | Prepare Overall Architecture, Design Pattern | Yes | 2 | 2009-08-11 | 2009-08-13
[5 empty] | Modular Breakdown and interface diagram | Yes | 2 | 2009-08-13 | 2009-08-17
Identification and selection of appropriate design Methodologies (e.g. structure module, OOD, Design patterns etc.)
Design Alternative consideration
[5 empty] | High Level Design (HLD) - Preparation | Yes | 3 | 2009-08-17 | 2009-08-20
Critical Data structures
[5 empty] | HLD Review | Yes | 2 | 2009-08-20 | 2009-08-24
[5 empty] | Bugzilla - Review Defect update (HLD) | Yes | 1 | 2009-08-24 | 2009-08-25
[5 empty] | Low Level Design (LLD) Pseudo code development | Yes | 7 | 2009-08-25 | 2009-09-03
[5 empty] | LLD Review | Yes | 2 | 2009-09-03 | 2009-09-07
[5 empty] | Bugzilla - Review Defect update (LLD) | Yes | 1 | 2009-09-07 | 2009-09-08
[5 empty] | SCM set-up for build version and release | Yes | 2 | 2009-09-08 | 2009-09-10
[5 empty] | Test Design and test cases generation | Yes | 2 | 2009-09-10 | 2009-09-14
[5 empty] | Update Bi-directional Traceability | Yes | 2 | 2009-09-14 | 2009-09-16
[5 empty] | Review Comment Analysis with team | Yes | 1 | 2009-09-16 | 2009-09-17
[5 empty] | Configuration Audit | Yes | 1 | 2009-09-17 | 2009-09-20
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 1 | 2009-09-20 | 2009-09-21
[5 empty] | Release - Architecture and Design | Yes | 1 | 2009-09-21 | 2009-09-22
CUT/Implementation | Coding, Reviews and Unit Testing | 27 | 2009-09-22 | 2009-10-29
[5 empty] | LAM - CUT /Implementation | Yes | 1 | 2009-09-22 | 2009-09-23
[5 empty] | Build Setup and Build procedure documentation/guidelines | Yes | 2 | 2009-09-23 | 2009-09-25
[5 empty] | Identification of inter module dependencies | Yes | 1 | 2009-09-25 | 2009-09-28
[5 empty] | Development of the code using appropriate method - structured programming, Object Oriented Programming, Design Pattern | Yes | 7 | 2009-09-28 | 2009-10-07
[5 empty] | Coding as per guidelines | Yes | 5 | 2009-10-07 | 2009-10-14
[5 empty] | Static Analysis of Code using - WiproStyle/Jtest/C++ Test/Lints/Other Tools | Yes | 1 | 2009-10-14 | 2009-10-15
[5 empty] | Review of Critical section of Code | Yes | 2 | 2009-10-15 | 2009-10-19
Bugzilla - Review comments update
[5 empty] | Preparation of Unit Test plan and test cases | Yes | 1 | 2009-10-19 | 2009-10-20
[5 empty] | Unit Testing of components using open source testing and debugging tools | Yes | 1 | 2009-10-20 | 2009-10-21
[5 empty] | Documentation and Packaging | Yes | 2 | 2009-10-21 | 2009-10-23
Update Bidirectional Traceability Matrix
[5 empty] | Configuration Audit | Yes | 1 | 2009-10-23 | 2009-10-26
[5 empty] | Review comment analysis with team | Yes | 1 | 2009-10-26 | 2009-10-27
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 1 | 2009-10-27 | 2009-10-28
[5 empty] | Release - Cut/Implementation | Yes | 1 | 2009-10-28 | 2009-10-29
System Integration and Testing | Integration and System Testing | 13 | 2009-10-29 | 2009-11-17
[5 empty] | LAM - System testing and Testing | Yes | 1 | 2009-10-29 | 2009-10-30
[5 empty] | Prepare System Test plan and test cases | Yes | 2 | 2009-10-30 | 2009-11-03
[5 empty] | Modular testing | Yes | 1 | 2009-11-03 | 2009-11-04
[5 empty] | Modular interface integration | Yes | 1 | 2009-11-04 | 2009-11-05
[5 empty] | Build and Release | Yes | 1 | 2009-11-05 | 2009-11-06
[5 empty] | Configuration Audit | Yes | 1 | 2009-11-06 | 2009-11-09
[5 empty] | System testing: Execution of test cases as per test plan in 2 cycles with bug fixing | Yes | 1 | 2009-11-09 | 2009-11-10
[5 empty] | Perform testing for - Functional testing, Performance testing , Reliability testing, Usability Testing, Load Testing, Volume and Stress Testing | Yes | 1 | 2009-11-10 | 2009-11-11
[5 empty] | Update test result and Traceability sheet | Yes | 1 | 2009-11-11 | 2009-11-12
[5 empty] | Test Result Analysis with Team | Yes | 1 | 2009-11-12 | 2009-11-13
[5 empty] | Project Presentation to KRCF & Wipro | Yes | 1 | 2009-11-13 | 2009-11-16
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 1 | 2009-11-16 | 2009-11-17
NA | White Paper | 6 | 2009-11-17 | 2009-11-25
[5 empty] | Preparation of While paper abstract and review | Yes | 1 | 2009-11-17 | 2009-11-18
[5 empty] | Study of the identified topics for white paper | Yes | 1 | 2009-11-18 | 2009-11-19
[5 empty] | Preparation White paper abstract | Yes | 2 | 2009-11-19 | 2009-11-23
[5 empty] | Final review of the White paper | Yes | 1 | 2009-11-23 | 2009-11-24
[5 empty] | Presentation of KRCF team | Yes | 1 | 2009-11-24 | 2009-11-25
Formulas:
End Date (DD-MON-YY) = [Start Date (DD-MON-YY)]+[Duration (Days)]
Start Date (DD-MON-YY) = [Start Date (DD-MON-YY), row below]
Start Date (DD-MON-YY) = [End Date (DD-MON-YY), row above]
Note on D4: ganesh: Overall Days for this phase
Note on E4: ganesh: Start date of this phase
Note on F4: ganesh: End Date of this phase

## Multimedia_VideoAnalytics
Waterfall Process Model Mapping | Project Execution Phase | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Activities | Applicable (Yes/No) | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Wipro Engineers Effort (PHRS) | Wipro Engineers Effort (Pdays) | KRCF Engineers Effort (PHRS) | KRCF Engineers Effort (Pdays)
Project Initiation and Planning | Project Preparedness Workshop (ppw) | 4 | 2009-06-25 | 2009-06-30
[5 empty] | Finalization & White paper generation of project titles | Y
[5 empty] | Briefing of project titles | Y
[5 empty] | Micro Project definition | Y
[5 empty] | Project Team Formation | Y | 1 |  |  |  | 1
[5 empty] | Project plan - work book preparation | Y | 2 |  |  |  | 2
[5 empty] | Kick-off Meeting for individual projects | Y | 1 |  |  |  | 5 |  | 12
Requirement Analysis | Requirement Gathering and Prototyping | 24 | 2009-07-01 | 2009-08-03
[5 empty] | LAM - Requirement Analysis | Y | 1 | 2009-07-01 | 2009-07-01 |  | 3 |  | 12
[5 empty] | Identification of Requirement Gathering Technique | Y
[5 empty] | Identification of Functional and Non Functional Requirements | Y | 5 | 2009-07-02 | 2009-07-08 |  | 15 |  | 60
[5 empty] | Identification of Performance Requirements of System | Y
[5 empty] | Inputs and Outputs to system | Y | 3 | 2009-07-09 | 2009-07-13 |  | 6 |  | 36
[5 empty] | User Interface (if any) and Data Requirements | Y | 2 | 2009-07-14 | 2009-07-15 |  | 4 |  | 16
[5 empty] | Internal External Interface Identification | Y
[5 empty] | Environmental Constraints | Y | 2 | 2009-07-14 | 2009-07-15 |  | 2 |  | 8
[5 empty] | Requirement Related to Safety, security, and reliability aspects | Y
[5 empty] | Saturatory and Regulatory Requirements (If any) | Y
[5 empty] | System/Business Use case generation | Y | 4 | 2009-07-16 | 2009-07-21 |  | 8 |  | 48
[5 empty] | Identification and prioritization of requirements | Y | 1 | 2009-07-22 | 2009-07-22 |  | 1 |  | 2
[5 empty] | Assigning Unique ID to each requirement | Y
[5 empty] | Preparation of Requirement Specification | Y | 3 | 2009-07-23 | 2009-07-27 |  | 3 |  | 12
[5 empty] | Preparation of Requirement Traceability Sheet | Y
[5 empty] | Requirements Review | Y | 2 | 2009-07-28 | 2009-07-29 |  | 1 |  | 4
[5 empty] | Bugzilla - Review defect update | Y
[5 empty] | Review comment analysis with team | Y
[5 empty] | Prototyping Critical Requirements | Y | 5 | 2009-07-23 | 2009-07-29 |  | 5 |  | 30
[5 empty] | Configuration Audit | Y | 1 | 2009-07-30 | 2009-07-30 |  | 1 |  | 2
[5 empty] | KRCF - Engineers Performance Appraisal | Y | 1 | 2009-07-31 | 2009-07-31 |  | 1 |  | 12
[5 empty] | Release - Requirement Analysis Phase | Y | 1 | 2009-08-03 | 2009-08-03 |  | 1 |  | 2
[5 empty] | Proof Of Concept for alternative approaches of critical requirements | Y | 44 | 2009-07-01 | 2009-08-31 |  | 66 |  | 0
Architecture and Design | Design | 32 | 2009-08-04 | 2009-09-16
[5 empty] | LAM - Architecture and Design | Y | 1 | 2009-08-04 | 2009-08-04 |  | 4 |  | 12
[5 empty] | Prepare Overall Architecture, Design Pattern | Y | 8 | 2009-08-05 | 2009-08-14 |  | 24 |  | 96
[5 empty] | Modular Breakdown and interface diagram | Y
[5 empty] | Identification and selection of appropriate design Methodologies (e.g. structure module, OOD, Design patterns etc.) | Y | 3 | 2009-08-17 | 2009-08-19 |  | 9 |  | 36
[5 empty] | Design Alternative consideration | Y
[5 empty] | High Level Design (HLD) - Preparation | Y | 4 | 2009-08-20 | 2009-08-25 |  | 12 |  | 32
[5 empty] | Critical Data structures | Y
[5 empty] | HLD Review | Y | 2 | 2009-08-26 | 2009-08-27 |  | 2 |  | 8
[5 empty] | Bugzilla - Review Defect update (HLD) | Y
[5 empty] | Low Level Design (LLD) Pseudo code development | Y | 5 | 2009-08-26 | 2009-09-01 |  | 15 |  | 40
[5 empty] | LLD Review | Y | 2 | 2009-09-02 | 2009-09-03 |  | 4 |  | 8
[5 empty] | Bugzilla - Review Defect update (LLD) | Y
[5 empty] | SCM set-up for build version and release | Y | 1 | 2009-09-04 | 2009-09-04 |  | 1 |  | 2
[5 empty] | Test Design and test cases generation | Y | 5 | 2009-09-03 | 2009-09-09 |  | 10 |  | 40
[5 empty] | Update Bi-directional Traceability | Y | 1 | 2009-09-10 | 2009-09-10 |  | 1 |  | 2
[5 empty] | Review Comment Analysis with team | Y | 1 | 2009-09-11 | 2009-09-11 |  | 2 |  | 6
[5 empty] | Configuration Audit | Y | 1 | 2009-09-14 | 2009-09-14 |  | 1 |  | 2
[5 empty] | KRCF - Engineers Performance Appraisal | Y | 1 | 2009-09-15 | 2009-09-15 |  | 1 |  | 12
[5 empty] | Release - Architecture and Design | Y | 1 | 2009-09-16 | 2009-09-16 |  | 1 |  | 2
CUT/Implementation | Coding, Reviews and Unit Testing | 25 | 2009-09-17 | 2009-10-21
[5 empty] | LAM - CUT /Implementation | Y | 0.5 | 2009-09-17 | 2009-09-17 |  | 2.5 |  | 6
[5 empty] | Build Setup and Build procedure documentation/guidelines | Y | 0.5 | 2009-09-17 | 2009-09-17 |  | 1 |  | 3
[5 empty] | Identification of inter module dependencies | Y | 2 | 2009-09-18 | 2009-09-21 |  | 6 |  | 16
[5 empty] | Development of the code using appropriate method - structured programming, Object Oriented Programming, Design Pattern | Y | 15 | 2009-09-22 | 2009-10-12 |  | 45 |  | 180
[5 empty] | Coding as per guidelines | Y
[5 empty] | Static Analysis of Code using - WiproStyle/Jtest/C++ Test/Lints/Other Tools | Y | 2 | 2009-10-13 | 2009-10-14 |  | 2 |  | 6
[5 empty] | Review of Critical section of Code | Y | 2 | 2009-10-13 | 2009-10-14 |  | 4 |  | 10
[5 empty] | Bugzilla - Review comments update | Y | 1 | 2009-10-15 | 2009-10-15 |  | 1 |  | 2
[5 empty] | Preparation of Unit Test plan and test cases | Y | 2 | 2009-10-13 | 2009-10-14 |  | 4 |  | 10
[5 empty] | Unit Testing of components using open source testing and debugging tools | Y | 4 | 2009-10-15 | 2009-10-20 |  | 8 |  | 24
[5 empty] | Documentation and Packaging | Y | 1 | 2009-10-15 | 2009-10-15 |  | 1 |  | 4
[5 empty] | Update Bidirectional Traceability Matrix | Y | 0.5 | 2009-10-16 | 2009-10-16 |  | 0.5 |  | 1
[5 empty] | Configuration Audit | Y | 1 | 2009-10-19 | 2009-10-19 |  | 1 |  | 2
[5 empty] | Review comment analysis with team | Y | 1 | 2009-10-20 | 2009-10-20 |  | 3 |  | 12
[5 empty] | KRCF - Engineers Performance Appraisal | Y | 1 | 2009-10-21 | 2009-10-21 |  | 1 |  | 12
[5 empty] | Release - Cut/Implementation | Y | 0.5 | 2009-10-21 | 2009-10-21 |  | 0.5 |  | 1
System Integration and Testing | Integration and System Testing | 15 | 2009-10-22 | 2009-11-11
|  | 100 |  |  | LAM - System testing and Testing | Y | 0.5 | 2009-10-22 | 2009-10-22 |  | 2.5 |  | 6
[5 empty] | Prepare System Test plan and test cases | Y | 2 | 2009-10-22 | 2009-10-23 |  | 6 |  | 16
[5 empty] | Modular testing | Y | 2 | 2009-10-26 | 2009-10-27 |  | 4 |  | 12
[5 empty] | Modular interface integration | Y | 1 | 2009-10-27 | 2009-10-27 |  | 2 |  | 6
[5 empty] | Build and Release | Y | 1 | 2009-10-28 | 2009-10-28 |  | 1 |  | 2
[5 empty] | Configuration Audit | Y | 0.5
[5 empty] | System testing: Execution of test cases as per test plan in 2 cycles with bug fixing | Y | 8 | 2009-10-29 | 2009-11-09 |  | 30 |  | 96
[5 empty] | Perform testing for - Functional testing, Performance testing , Reliability testing, Usability Testing, Load Testing, Volume and Stress Testing | Y
[5 empty] | Update test result and Traceability sheet | Y | 1 | 2009-11-10 | 2009-11-10 |  | 2 |  | 4
[5 empty] | Test Result Analysis with Team | Y | 1 | 2009-11-10 | 2009-11-10 |  | 2 |  | 6
[5 empty] | Project Presentation to KRCF & Wipro | Y | 1 | 2009-11-11 | 2009-11-11 |  | 2 |  | 12
[5 empty] | KRCF - Engineers Performance Appraisal | Y | 1 | 2009-11-11 | 2009-11-11 |  | 1 |  | 12
NA | White Paper | 12 | 2009-11-12 | 2009-11-27
[5 empty] | Preparation of White paper abstract and review | Y | 2 | 2009-11-12 | 2009-11-13 |  | 4 |  | 16
[5 empty] | Study of the identified topics for white paper | Y | 5 | 2009-11-16 | 2009-11-20 |  | 10 |  | 40
[5 empty] | Preparation White paper | Y | 2 | 2009-11-23 | 2009-11-24 |  | 4 |  | 16
[5 empty] | Final review of the White paper | Y | 2 | 2009-11-25 | 2009-11-26 |  | 4 |  | 16
[5 empty] | Presentation of KRCF team | Y | 1 | 2009-11-27 | 2009-11-27 |  | 1 |  | 8
Note on D4: ganesh: Overall Days for this phase
Note on E4: ganesh: Start date of this phase
Note on F4: ganesh: End Date of this phase
Note on D3: arunkus: Working Days
Note on G34: : This is parallel 2 months activity which will continue along with RS and design phase. This will also include prototyping of some of requirements

## Multimedia_ALCFlute
Iteration 1
Waterfall Process Model Mapping 1 | Project Execution Phase | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Activities | Applicable (Yes/No) | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Wipro Engineers Effort (Pdays) | KRCF Engineers Effort (Pdays)
Project Initiation and Planning | Project Preparedness Workshop (ppw) | 3 | 2009-06-26 | 2009-06-30
[5 empty] | Finalization & White paper generation of project titles | Yes | 1
[5 empty] | Briefing of project titles | Yes | 1
[5 empty] | Micro Project definition | Yes | 1
[5 empty] | Project Team Formation | Yes | 1
[5 empty] | Project plan - work book preparation | Yes | 3
[5 empty] | Kick-off Meeting for individual projects | Yes | 2
Requirement Analysis | Requirement Gathering and Prototyping | 16 | 2009-07-01 | 2009-07-22
[5 empty] | LAM - Requirement Analysis | Yes | 2 | 2009-07-01 | 2009-07-02 | 6 | 12
[5 empty] | Identification of Requirement Gathering Technique | Yes | 1 | 2009-07-03 | 2009-07-03 | 3 | 6
[5 empty] | Identification of Functional and Non Functional Requirements | Yes | 2 | 2009-07-06 | 2009-07-07 | 6 | 12
[5 empty] | Identification of Performance Requirements of System | Yes | 1 | 2009-07-08 | 2009-07-08 | 3 | 6
[5 empty] | Inputs and Outputs to system | Yes | 1 | 2009-07-09 | 2009-07-09 | 3 | 6
[5 empty] | User Interface (if any) and Data Requirements | Yes | 1 | 2009-07-10 | 2009-07-10 | 3 | 6
[5 empty] | Internal External Interface Identification | Yes | 2 | 2009-07-13 | 2009-07-14 | 6 | 12
[5 empty] | Environmental Constraints | Yes | 1 | 2009-07-15 | 2009-07-15 | 3 | 6
[5 empty] | Requirement Related to Safety, security, and reliability aspects | Yes | 1 | 2009-07-16 | 2009-07-16 | 3 | 6
[5 empty] | Saturatory and Regulatory Requirements (If any) | NA
[5 empty] | System/Business Use case generation | NA
[5 empty] | Identification and prioritization of requirements | NA
[5 empty] | Assigning Unique ID to each requirement | NA
[5 empty] | Preparation of Requirement Specification | Yes | 1 | 2009-07-17 | 2009-07-17 | 3 | 6
[5 empty] | Preparation of Requirement Traceability Sheet | NA
[5 empty] | Requirements Review | Yes | 1 | 2009-07-20 | 2009-07-20 | 3 | 6
[5 empty] | Bugzilla - Review defect update | NA
[5 empty] | Review comment analysis with team | Yes | 1 | 2009-07-21 | 2009-07-21 | 3 | 6
[5 empty] | Prototyping Critical Requirements | NA
[5 empty] | Configuration Audit | NA
[5 empty] | KRCF - Engineers Performance Appraisal | NA
[5 empty] | Release - Requirement Analysis Phase | Yes | 1 | 2009-07-22 | 2009-07-22 | 3 | 6
Architecture and Design | Design | 15 | 2009-07-23 | 2009-08-12
[5 empty] | LAM - Architecture and Design | Yes | 1 | 2009-07-23 | 2009-07-23 | 3 | 6
[5 empty] | Prepare Overall Architecture, Design Pattern | Yes | 3 | 2009-07-24 | 2009-07-28 | 9 | 18
[5 empty] | Modular Breakdown and interface diagram | Yes | 1 | 2009-07-29 | 2009-07-29 | 3 | 6
[5 empty] | Identification and selection of appropriate design Methodologies (e.g. structure module, OOD, Design patterns etc.) | Yes | 2 | 2009-07-30 | 2009-07-31 | 6 | 12
[5 empty] | Design Alternative consideration | Yes | 1 | 2009-08-03 | 2009-08-03 | 3 | 6
[5 empty] | High Level Design (HLD) - Preparation | Yes | 1 | 2009-08-04 | 2009-08-04 | 3 | 6
[5 empty] | Critical Data structures | Yes | 1 | 2009-08-05 | 2009-08-05 | 3 | 6
[5 empty] | HLD Review | NA
[5 empty] | Bugzilla - Review Defect update (HLD) | NA
[5 empty] | Low Level Design (LLD) Pseudo code development | Yes | 1 | 2009-08-06 | 2009-08-06 | 3 | 6
[5 empty] | LLD Review | NA
[5 empty] | Bugzilla - Review Defect update (LLD) | NA
[5 empty] | SCM set-up for build version and release | Yes | 1 | 2009-08-07 | 2009-08-07 | 3 | 6
[5 empty] | Test Design and test cases generation | Yes | 1 | 2009-08-10 | 2009-08-10 | 3 | 6
[5 empty] | Update Bi-directional Traceability | NA
[5 empty] | Review Comment Analysis with team | Yes | 1 | 2009-08-11 | 2009-08-11 | 3 | 6
[5 empty] | Configuration Audit | NA
[5 empty] | KRCF - Engineers Performance Appraisal | NA
[5 empty] | Release - Architecture and Design | Yes | 1 | 2009-08-12 | 2009-08-12 | 3 | 6
CUT/Implementation | Coding, Reviews and Unit Testing | 15 | 2009-08-13 | 2009-09-03
[5 empty] | LAM - CUT /Implementation | Yes | 1 | 2009-08-13 | 2009-08-13 | 3 | 6
[5 empty] | Build Setup and Build procedure documentation/guidelines | Yes | 1 | 2009-08-14 | 2009-08-14 | 3 | 6
[5 empty] | Identification of inter module dependencies | Yes | 2 | 2009-08-17 | 2009-08-18 | 6 | 12
[5 empty] | Development of the code using appropriate method - structured programming, Object Oriented Programming, Design Pattern | Yes | 5 | 2009-08-19 | 2009-08-25 | 15 | 30
[5 empty] | Coding as per guidelines | Yes | 1 | 2009-08-26 | 2009-08-26 | 3 | 6
[5 empty] | Static Analysis of Code using - WiproStyle/Jtest/C++ Test/Lints/Other Tools | NA
[5 empty] | Review of Critical section of Code | Yes | 1 | 2009-08-27 | 2009-08-27 | 3 | 6
[5 empty] | Bugzilla - Review comments update | NA
[5 empty] | Preparation of Unit Test plan and test cases | Yes | 1 | 2009-08-28 | 2009-08-28 | 3 | 6
[5 empty] | Unit Testing of components using open source testing and debugging tools | Yes | 1 | 2009-09-01 | 2009-09-01 | 3 | 6
[5 empty] | Documentation and Packaging | Yes | 1 | 2009-09-02 | 2009-09-02 | 3 | 6
[5 empty] | Update Bidirectional Traceability Matrix | NA
[5 empty] | Configuration Audit | NA
[5 empty] | Review comment analysis with team | Yes | 0.5 | 2009-09-03 | 2009-09-03 | 3 | 6
[5 empty] | KRCF - Engineers Performance Appraisal | NA
[5 empty] | Release - Cut/Implementation | Yes | 0.5 | 2009-09-03 | 2009-09-03 | 2 | 4
System Integration and Testing | Integration and System Testing | 21 | 2009-09-04 | 2009-10-02
[5 empty] | LAM - System testing and Testing | Yes | 1 | 2009-09-04 | 2009-09-04 | 3 | 6
[5 empty] | Prepare System Test plan and test cases | Yes | 3 | 2009-09-07 | 2009-09-09 | 9 | 18
[5 empty] | Modular testing | Yes | 3 | 2009-09-10 | 2009-09-14 | 9 | 18
[5 empty] | Modular interface integration | Yes | 3 | 2009-09-15 | 2009-09-17 | 9 | 18
[5 empty] | Build and Release | Yes | 1 | 2009-09-18 | 2009-09-18 | 3 | 6
[5 empty] | Configuration Audit | Yes | 1 | 2009-09-21 | 2009-09-21 | 3 | 6
[5 empty] | System testing: Execution of test cases as per test plan in 2 cycles with bug fixing | Yes | 2 | 2009-09-22 | 2009-09-23 | 6 | 12
[5 empty] | Perform testing for - Functional testing, Performance testing , Reliability testing, Usability Testing, Load Testing, Volume and Stress Testing | Yes | 3 | 2009-09-24 | 2009-09-28 | 9 | 20
[5 empty] | Update test result and Traceability sheet | Yes | 1 | 2009-09-29 | 2009-09-29 | 3 | 6
[5 empty] | Test Result Analysis with Team | Yes | 1 | 2009-09-30 | 2009-09-30 | 3 | 6
[5 empty] | Project Presentation to KRCF & Wipro | Yes | 1 | 2009-10-01 | 2009-10-01 | 3 | 6
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 1 | 2009-10-02 | 2009-10-02 | 3 | 6
NA | White Paper | 10 | 2009-08-25 | 2009-09-08
[5 empty] | Preparation of While paper abstract and review | Yes
[5 empty] | Study of the identified topics for white paper | Yes
[5 empty] | Preparation White paper abstract | Yes
[5 empty] | Final review of the White paper | Yes
[5 empty] | Presentation of KRCF team | Yes
Iteration 2
Waterfall Process Model Mapping 2 | Project Execution Phase | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Activities | Applicable (Yes/No) | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Wipro Engineers Effort (Pdays) | Wipro Engineers Effort (PHRS)
NA | Study/Scope | 1 | 2009-10-05 | 2009-10-05
[5 empty] | Finalization & White paper generation of project titles | NA
[5 empty] | Briefing of project titles | Yes | 1 Day for all | 2009-10-05 | 2009-10-05 | 3 | 6
[5 empty] | Micro Project definition | Yes
[5 empty] | Project Team Formation | Yes
[5 empty] | Project plan - work book preparation | Yes
[5 empty] | Kick-off Meeting for individual projects | Yes
Requirement Analysis | Requirement Gathering and Prototyping | 7 | 2009-10-06 | 2009-10-14
[5 empty] | LAM - Requirement Analysis | Yes
[5 empty] | Identification of Requirement Gathering Technique | Yes
[5 empty] | Identification of Functional and Non Functional Requirements | Yes
[5 empty] | Identification of Performance Requirements of System | Yes
[5 empty] | Inputs and Outputs to system | Yes
[5 empty] | User Interface (if any) and Data Requirements | Yes
[5 empty] | Internal External Interface Identification | Yes
[5 empty] | Environmental Constraints | Yes
[5 empty] | Requirement Related to Safety, security, and reliability aspects | Yes | 7 Days (For all the tasks) | 2009-10-06 | 2009-10-14 | 21 | 42
[5 empty] | Saturatory and Regulatory Requirements (If any) | NA
[5 empty] | System/Business Use case generation | NA
[5 empty] | Identification and prioritization of requirements | NA
[5 empty] | Assigning Unique ID to each requirement | NA
[5 empty] | Preparation of Requirement Specification | Yes
[5 empty] | Preparation of Requirement Traceability Sheet | NA
[5 empty] | Requirements Review | Yes
[5 empty] | Bugzilla - Review defect update | NA
[5 empty] | Review comment analysis with team | Yes
[5 empty] | Prototyping Critical Requirements | NA
[5 empty] | Configuration Audit | NA
[5 empty] | KRCF - Engineers Performance Appraisal | NA
[5 empty] | Release - Requirement Analysis Phase | Yes
Architecture and Design | Design | 10 | 2009-10-15 | 2009-10-28
[5 empty] | LAM - Architecture and Design | Yes
[5 empty] | Prepare Overall Architecture, Design Pattern | Yes
[5 empty] | Modular Breakdown and interface diagram | Yes
[5 empty] | Identification and selection of appropriate design Methodologies (e.g. structure module, OOD, Design patterns etc.) | Yes | 10 Dayas (For all the tasks) | 2009-10-15 | 2009-10-28 | 30 | 60
[5 empty] | Design Alternative consideration | Yes
[5 empty] | High Level Design (HLD) - Preparation | Yes
[5 empty] | Critical Data structures | Yes
[5 empty] | HLD Review | NA
[5 empty] | Bugzilla - Review Defect update (HLD) | NA
[5 empty] | Low Level Design (LLD) Pseudo code development | Yes
[5 empty] | LLD Review | NA
[5 empty] | Bugzilla - Review Defect update (LLD) | NA
[5 empty] | SCM set-up for build version and release | Yes
[5 empty] | Test Design and test cases generation | Yes
[5 empty] | Update Bi-directional Traceability | NA
[5 empty] | Review Comment Analysis with team | Yes
[5 empty] | Configuration Audit | NA
[5 empty] | KRCF - Engineers Performance Appraisal | NA
[5 empty] | Release - Architecture and Design | Yes
CUT/Implementation | Coding, Reviews and Unit Testing | 8 | 2009-10-29 | 2009-11-09
[5 empty] | LAM - CUT /Implementation | Yes
[5 empty] | Build Setup and Build procedure documentation/guidelines | Yes
[5 empty] | Identification of inter module dependencies | Yes
[5 empty] | Development of the code using appropriate method - structured programming, Object Oriented Programming, Design Pattern | Yes | 8 Dayas (For all the tasks) | 2009-10-29 | 2009-11-09 | 24 | 48
[5 empty] | Coding as per guidelines | Yes
[5 empty] | Static Analysis of Code using - WiproStyle/Jtest/C++ Test/Lints/Other Tools | NA
[5 empty] | Review of Critical section of Code | Yes
[5 empty] | Bugzilla - Review comments update | NA
[5 empty] | Preparation of Unit Test plan and test cases | Yes
[5 empty] | Unit Testing of components using open source testing and debugging tools | Yes
[5 empty] | Documentation and Packaging | Yes
[5 empty] | Update Bidirectional Traceability Matrix | NA
[5 empty] | Configuration Audit | NA
[5 empty] | Review comment analysis with team | Yes
[5 empty] | KRCF - Engineers Performance Appraisal | NA
[5 empty] | Release - Cut/Implementation | Yes
System Integration and Testing | Integration and System Testing | 4 | 2009-11-09 | 2009-11-13
[5 empty] | LAM - System testing and Testing | Yes
[5 empty] | Prepare System Test plan and test cases | Yes
[5 empty] | Modular testing | Yes
[5 empty] | Modular interface integration | Yes
[5 empty] | Build and Release | Yes
[5 empty] | Configuration Audit | Yes
[5 empty] | System testing: Execution of test cases as per test plan in 2 cycles with bug fixing | Yes
[5 empty] | Perform testing for - Functional testing, Performance testing , Reliability testing, Usability Testing, Load Testing, Volume and Stress Testing | Yes | 4 Days (for all the tasks) | 2009-11-09 | 2009-11-13 | 12 | 24
[5 empty] | Update test result and Traceability sheet | Yes
[5 empty] | Test Result Analysis with Team | Yes
[5 empty] | Project Presentation to KRCF & Wipro | Yes
[5 empty] | KRCF - Engineers Performance Appraisal | Yes
Note on D4: ganesh: Overall Days for this phase
Note on E4: ganesh: Start date of this phase
Note on F4: ganesh: End Date of this phase
Note on D94: ganesh: Overall Days for this phase
Note on E94: ganesh: Start date of this phase
Note on F94: ganesh: End Date of this phase
Note on J96: ganesh: Start date of this phase
Note on K96: ganesh: Start date of this phase

## DBMS_PRJ1_ShortCut
Waterfall Process Model Mapping | Project Execution Phase | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Activities | Applicable (Yes/No) | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Wipro Engineers Effort (PHRS) | Wipro Engineers Effort (Pdays)
Project Initiation and Planning | Project Preparedness Workshop (ppw) | 15 | 2009-06-22 | 2009-06-30
Finalization & White paper generation of project titles
Briefing of project titles
Micro Project definition
Project Team Formation
Project plan - work book preparation
Kick-off Meeting for individual projects
Requirement Analysis | Requirement Gathering and Prototyping | 31 | 2009-07-08 | 2009-08-11
[5 empty] | LAM - Requirement Analysis | Yes | 1 | 2009-08-07 | 2009-08-07 |  | 0.5
[5 empty] | Identification of Requirement Gathering Technique | No | Will be done in Func requirement phase
[5 empty] | Identification of Functional and Non Functional Requirements | Yes | 2 | 2009-08-07 | 2009-09-07 |  | 1
[5 empty] | Identification of Performance Requirements of System | No | Performance requirement is not applicable to dbms projects
[5 empty] | Inputs and Outputs to system | Yes | 2 | 2009-10-07 | 13/7/2009 |  | 1
[5 empty] | User Interface (if any) and Data Requirements | Yes | 1 | 14/7/2009 | 14/7/2009 |  | 0.5
[5 empty] | Internal External Interface Identification | Yes | 1 | 15/7/2009 | 15/7/2009 |  | 0.5
[5 empty] | Environmental Constraints | No | Environmental Constraints not applicable
[5 empty] | Requirement Related to Safety, security, and reliability aspects | No | Requirement Related to Safety, security, and reliability aspects not applicable
[5 empty] | Saturatory and Regulatory Requirements (If any) | NA
[5 empty] | System/Business Use case generation | Yes | 6 | 17/07/2009 | 24/07/2009 |  | 3
[5 empty] | Identification and prioritization of requirements | yes | 2 | 27/07/09 | 28/07/2009 |  | 1
[5 empty] | Assigning Unique ID to each requirement | yes | 1 | 29/07/09 | 29/07/2009 |  | 1
[5 empty] | Preparation of Requirement Specification | Yes | 4 | 30/07/2009 | 3/8/2009 |  | 2
[5 empty] | Preparation of Requirement Traceability Sheet | Yes | 1 | 4/08/2009 | 4/08/2009 |  | 0.5
[5 empty] | Requirements Review | Yes | 2 | 5/08/2009 | 10/08/2009 |  | 0.5
[5 empty] | Bugzilla - Review defect update | Yes |  |  |  |  | 0.5
[5 empty] | Review comment analysis with team | Yes |  |  |  |  | 0.5
[5 empty] | Prototyping Critical Requirements | Yes |  |  |  |  | 1
[5 empty] | Configuration Audit | Yes | 1 | 11/08/2009 | 11/08/2009 |  | 2
[5 empty] | KRCF - Engineers Performance Appraisal | Yes |  |  |  |  | 0.5
[5 empty] | Release - Requirement Analysis Phase | yes |  |  |  |  | 0.5
Architecture and Design | Design | 33 | 2009-08-12 | 2009-09-30 | [6 empty] | 1
[5 empty] | LAM - Architecture and Design | Yes | 1 | 2009-12-08 | 405397
[5 empty] | Prepare Overall Architecture, Design Pattern | Yes | 8 | 13/8/2009 | 22/8/2009 |  | 0.5
[5 empty] | Modular Breakdown and interface diagram | Yes | 4 | 25/8/2009 | 28/09/2009 |  | 3
[5 empty] | Identification and selection of appropriate design Methodologies (e.g. structure module, OOD, Design patterns etc.) | yes | 2 | 29/9/2009 | 2009-01-09 |  | 1
[5 empty] | Design Alternative consideration | [5 empty] | 1
[5 empty] | High Level Design (HLD) - Preparation | Yes | 4 | 2/9/2009 | 8/9/2009 |  | 2
[5 empty] | Critical Data structures | Yes | 1 | 10/9/09 | 2009-10-09 |  | 2
[5 empty] | HLD Review | Yes | 0.5 | 11/9/09 | 11/9/09 |  | 1
[5 empty] | Bugzilla - Review Defect update (HLD) | Yes | 0.5 | 11/9/09 | 11/9/09 |  | 0.5
[5 empty] | Low Level Design (LLD) Pseudo code development | Yes | 2 | 12/9/09 | 15/09/09 |  | 1
[5 empty] | LLD Review | Yes | 1 | 16/09/2009 | 16/09/2009 |  | 2
[5 empty] | Bugzilla - Review Defect update (LLD) | yes | 0.5 | 16/9/2009 | 16/9/2009 |  | 1
[5 empty] | SCM set-up for build version and release | Yes | 4 | 17/09/2009 | 19/09/2009 |  | 2
[5 empty] | Test Design and test cases generation | Yes | 2 | 22/09/2009 | 23/09/2009 |  | 1
[5 empty] | Update Bi-directional Traceability | Yes | 1 | 24/09/2009 | 24/09/2009 |  | 1
[5 empty] | Review Comment Analysis with team | Yes | 1 | 25/09/2009 | 25/09/2009 |  | 0.5
[5 empty] | Configuration Audit | Yes | 1 | 26/08/2009 | 26/09/2009 |  | 0.5
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 1 | 29/09/2009 | 29/09/2009 |  | 0.5
[5 empty] | Release - Architecture and Design | Yes |  | 30/09/2009 | 30/09/2009 |  | 0.5
CUT/Implementation | Coding, Reviews and Unit Testing | 25 | 2009-10-01 | 2009-03-07
[5 empty] | LAM - CUT /Implementation | Yes | 0.5 | 2009-01-10 | 2009-01-10
[5 empty] | Build Setup and Build procedure documentation/guidelines | Yes | 2 | 2009-01-10 | 2009-02-10 |  | 1
[5 empty] | Identification of inter module dependencies | Yes | 2 | 2009-03-10 | 2009-06-10 |  | 1
[5 empty] | Development of the code using appropriate method - structured programming, Object Oriented Programming, Design Pattern | Yes | 10 | 2009-07-10 | 21/10/2009 |  | 5
[5 empty] | Coding as per guidelines | yes | 0.5 | 21/10/2009 | 21/10/2009 |  | 10
[5 empty] | Static Analysis of Code using - WiproStyle/Jtest/C++ Test/Lints/Other Tools | No | Deep check is planned use and it is covered in Development phase |  |  |  | 0.5
[5 empty] | Review of Critical section of Code | yes | 2 | 22/10/2009 | 23/10/2009 |  | 1
[5 empty] | Bugzilla - Review comments update | yes | 0.5 | 23/10/2009 | 23/10/2009 |  | 2
[5 empty] | Preparation of Unit Test plan and test cases | Yes | 2 | 24/10/2009 | 27/10/2009 |  | 1
[5 empty] | Unit Testing of components using open source testing and debugging tools | Yes | 1 | 28/10/2009 | 28/10/2009 |  | 0.5
[5 empty] | Documentation and Packaging | Yes | 2 | 29/10/2009 | 30/10/2009 |  | 1
[5 empty] | Update Bidirectional Traceability Matrix | Yes | 0.5 | 31/10/2009 | 31/10/2009 |  | 0.5
[5 empty] | Configuration Audit | Yes | 0.5 | 31/11/2009 | 31/10/2009 |  | 0.5
[5 empty] | Review comment analysis with team | Yes | 0.5 | 2009-03-11 | 2009-03-11 |  | 0.5
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 0.5 | 2009-03-11 | 2009-03-11 |  | 0.5
[5 empty] | Release - Cut/Implementation | Yes | 0.5 | 2009-03-11 | 2009-03-11 |  | 0.5
System Integration and Testing | Integration and System Testing | 10 | 2009-11-03 | 2009-11-14 | [6 empty] | 0.5
[5 empty] | LAM - System testing and Testing | Yes | 0.5 | 2009-04-11 | 2009-04-11
[5 empty] | Prepare System Test plan and test cases | Yes | 2 | 2009-04-11 | 4/11/2009 |  | 0.5
[5 empty] | Modular testing | No |  |  |  |  | 1
[5 empty] | Modular interface integration | No
[5 empty] | Build and Release | Yes | 2 | 5/11/2009 | 6/11/2009 |  | 1
[5 empty] | Configuration Audit | Yes | 1 | 7/77/2009 | 7/11/2009 |  | 0.5
[5 empty] | System testing: Execution of test cases as per test plan in 2 cycles with bug fixing | Yes | 2 | 10/11/2009 | 11/11/2009 |  | 1
[5 empty] | Perform testing for - Functional testing, Performance testing , Reliability testing, Usability Testing, Load Testing, Volume and Stress Testing | No | Not applicable for DBMS projects. |  |  |  | 10
[5 empty] | Update test result and Traceability sheet | Yes | 1 | 12/11/200 | 12/11/2009 |  | 0.5
[5 empty] | Test Result Analysis with Team | Yes | 1 | 13/11/2009 | 13/11/2009 |  | 0.5
[5 empty] | Project Presentation to KRCF & Wipro | Yes | 1 | 14/11/2009 | 14/11/2009 |  | 0.5
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 0.5 | 14/11/2009 | 14/11/2009 |  | 2
NA | White Paper | 5 | 2009-11-15 | 2009-11-21 | [6 empty] | 1
[5 empty] | Preparation of While paper abstract and review | Yes | 1 | 17/11/2009 | 17/11/2009
[5 empty] | Study of the identified topics for white paper | Yes | 1 | 18/11/2009 | 18/11/2009 |  | 0.5
[5 empty] | Preparation White paper abstract | Yes | 1 | 19/11/2009 | 19/11/2009 |  | 0.5
[5 empty] | Final review of the White paper | Yes | 1 | 20/11/2009 | 20/11/2009 |  | 0.5
[5 empty] | Presentation of KRCF team | Yes | 1 | 21/11/2009 | 21/11/2009 |  | 0.5
1
Note on D4: ganesh: Overall Days for this phase
Note on E4: ganesh: Start date of this phase
Note on F4: ganesh: End Date of this phase

## DBMS_PRJ2_DT
Waterfall Process Model Mapping | Project Execution Phase | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Activities | Applicable (Yes/No) | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Wipro Engineers Effort (PHRS) | Wipro Engineers Effort (Pdays)
Project Initiation and Planning | Project Preparedness Workshop (ppw) | 15 | 2009-06-22 | 2009-06-30
Finalization & White paper generation of project titles
Briefing of project titles
Micro Project definition
Project Team Formation
Project plan - work book preparation
Kick-off Meeting for individual projects
Requirement Analysis | Requirement Gathering and Prototyping | 31 | 2009-07-08 | 2009-08-11
[5 empty] | LAM - Requirement Analysis | Yes | 1 | 2009-08-07 | 2009-08-07 |  | 0.5
[5 empty] | Identification of Requirement Gathering Technique | No | Will be done in Func requirement phase
[5 empty] | Identification of Functional and Non Functional Requirements | Yes | 2 | 2009-08-07 | 2009-09-07 |  | 1
[5 empty] | Identification of Performance Requirements of System | No | Performance requirement is not applicable to dbms projects
[5 empty] | Inputs and Outputs to system | Yes | 2 | 2009-10-07 | 13/7/2009 |  | 1
[5 empty] | User Interface (if any) and Data Requirements | Yes | 1 | 14/7/2009 | 14/7/2009 |  | 0.5
[5 empty] | Internal External Interface Identification | Yes | 1 | 15/7/2009 | 15/7/2009 |  | 0.5
[5 empty] | Environmental Constraints | No | Environmental Constraints not applicable
[5 empty] | Requirement Related to Safety, security, and reliability aspects | No | Requirement Related to Safety, security, and reliability aspects not applicable
[5 empty] | Saturatory and Regulatory Requirements (If any) | NA
[5 empty] | System/Business Use case generation | Yes | 7 | 16/07/2009 | 24/07/2009 |  | 3
[5 empty] | Identification and prioritization of requirements | yes | 2 | 27/07/09 | 28/07/2009 |  | 1
[5 empty] | Assigning Unique ID to each requirement | yes | 1 | 29/07/09 | 29/07/2009 |  | 1
[5 empty] | Preparation of Requirement Specification | Yes | 4 | 30/07/2009 | 3/8/2009 |  | 2
[5 empty] | Preparation of Requirement Traceability Sheet | Yes | 1 | 4/08/2009 | 4/08/2009 |  | 0.5
[5 empty] | Requirements Review | Yes | 2 | 5/08/2009 | 10/08/2009 |  | 0.5
[5 empty] | Bugzilla - Review defect update | Yes |  |  |  |  | 0.5
[5 empty] | Review comment analysis with team | Yes |  |  |  |  | 0.5
[5 empty] | Prototyping Critical Requirements | Yes |  |  |  |  | 1
[5 empty] | Configuration Audit | Yes | 1 | 11/08/2009 | 11/08/2009 |  | 2
[5 empty] | KRCF - Engineers Performance Appraisal | Yes |  |  |  |  | 0.5
[5 empty] | Release - Requirement Analysis Phase | yes |  |  |  |  | 0.5
Architecture and Design | Design | 33 | 2009-08-12 | 2009-09-30 | [6 empty] | 1
[5 empty] | LAM - Architecture and Design | Yes | 1 | 2009-12-08 | 405397
[5 empty] | Prepare Overall Architecture, Design Pattern | Yes | 8 | 13/8/2009 | 22/8/2009 |  | 0.5
[5 empty] | Modular Breakdown and interface diagram | Yes | 4 | 25/8/2009 | 28/09/2009 |  | 3
[5 empty] | Identification and selection of appropriate design Methodologies (e.g. structure module, OOD, Design patterns etc.) | yes | 2 | 29/9/2009 | 2009-01-09 |  | 1
[5 empty] | Design Alternative consideration | n
[5 empty] | High Level Design (HLD) - Preparation | Yes | 5 | 2/9/2009 | 8/9/2009 |  | 2
[5 empty] | Critical Data structures | Yes | 1 | 10/9/09 | 2009-10-09 |  | 2
[5 empty] | HLD Review | Yes | 0.5 | 11/9/09 | 11/9/09 |  | 1
[5 empty] | Bugzilla - Review Defect update (HLD) | Yes | 0.5 | 11/9/09 | 11/9/09 |  | 0.5
[5 empty] | Low Level Design (LLD) Pseudo code development | Yes | 2 | 12/9/09 | 15/09/09 |  | 1
[5 empty] | LLD Review | Yes | 1 | 16/09/2009 | 16/09/2009 |  | 2
[5 empty] | Bugzilla - Review Defect update (LLD) | yes | 0.5 | 16/9/2009 | 16/9/2009 |  | 1
[5 empty] | SCM set-up for build version and release | Yes | 4 | 17/09/2009 | 19/09/2009 |  | 2
[5 empty] | Test Design and test cases generation | Yes | 2 | 22/09/2009 | 23/09/2009 |  | 1
[5 empty] | Update Bi-directional Traceability | Yes | 1 | 24/09/2009 | 24/09/2009 |  | 1
[5 empty] | Review Comment Analysis with team | Yes | 1 | 25/09/2009 | 25/09/2009 |  | 0.5
[5 empty] | Configuration Audit | Yes | 1 | 26/08/2009 | 26/09/2009 |  | 0.5
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 1 | 29/09/2009 | 29/09/2009 |  | 0.5
[5 empty] | Release - Architecture and Design | Yes |  | 30/09/2009 | 30/09/2009 |  | 0.5
CUT/Implementation | Coding, Reviews and Unit Testing | 25 | 2009-10-01 | 2009-03-07
[5 empty] | LAM - CUT /Implementation | Yes | 0.5 | 2009-01-10 | 2009-01-10
[5 empty] | Build Setup and Build procedure documentation/guidelines | Yes | 2 | 2009-01-10 | 2009-02-10 |  | 1
[5 empty] | Identification of inter module dependencies | Yes | 2 | 2009-03-10 | 2009-06-10 |  | 1
[5 empty] | Development of the code using appropriate method - structured programming, Object Oriented Programming, Design Pattern | Yes | 10 | 2009-07-10 | 21/10/2009 |  | 5
[5 empty] | Coding as per guidelines | yes | 0.5 | 21/10/2009 | 21/10/2009 |  | 10
[5 empty] | Static Analysis of Code using - WiproStyle/Jtest/C++ Test/Lints/Other Tools | No | Deep check is planned use and it is covered in Development phase |  |  |  | 0.5
[5 empty] | Review of Critical section of Code | yes | 2 | 22/10/2009 | 23/10/2009 |  | 1
[5 empty] | Bugzilla - Review comments update | yes | 0.5 | 23/10/2009 | 23/10/2009 |  | 2
[5 empty] | Preparation of Unit Test plan and test cases | Yes | 2 | 24/10/2009 | 27/10/2009 |  | 1
[5 empty] | Unit Testing of components using open source testing and debugging tools | Yes | 1 | 28/10/2009 | 28/10/2009 |  | 0.5
[5 empty] | Documentation and Packaging | Yes | 2 | 29/10/2009 | 30/10/2009 |  | 1
[5 empty] | Update Bidirectional Traceability Matrix | Yes | 0.5 | 31/10/2009 | 31/10/2009 |  | 0.5
[5 empty] | Configuration Audit | Yes | 0.5 | 31/11/2009 | 31/10/2009 |  | 0.5
[5 empty] | Review comment analysis with team | Yes | 0.5 | 2009-03-11 | 2009-03-11 |  | 0.5
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 0.5 | 2009-03-11 | 2009-03-11 |  | 0.5
[5 empty] | Release - Cut/Implementation | Yes | 0.5 | 2009-03-11 | 2009-03-11 |  | 0.5
System Integration and Testing | Integration and System Testing | 10 | 2009-11-03 | 2009-11-14 | [6 empty] | 0.5
[5 empty] | LAM - System testing and Testing | Yes | 0.5 | 2009-04-11 | 2009-04-11
[5 empty] | Prepare System Test plan and test cases | Yes | 2 | 2009-04-11 | 4/11/2009 |  | 0.5
[5 empty] | Modular testing | No |  |  |  |  | 1
[5 empty] | Modular interface integration | No
[5 empty] | Build and Release | Yes | 2 | 5/11/2009 | 6/11/2009 |  | 1
[5 empty] | Configuration Audit | Yes | 1 | 7/77/2009 | 7/11/2009 |  | 0.5
[5 empty] | System testing: Execution of test cases as per test plan in 2 cycles with bug fixing | Yes | 2 | 10/11/2009 | 11/11/2009 |  | 1
[5 empty] | Perform testing for - Functional testing, Performance testing , Reliability testing, Usability Testing, Load Testing, Volume and Stress Testing | No | Not applicable for DBMS projects. |  |  |  | 10
[5 empty] | Update test result and Traceability sheet | Yes | 1 | 12/11/200 | 12/11/2009 |  | 0.5
[5 empty] | Test Result Analysis with Team | Yes | 1 | 13/11/2009 | 13/11/2009 |  | 0.5
[5 empty] | Project Presentation to KRCF & Wipro | Yes | 1 | 14/11/2009 | 14/11/2009 |  | 0.5
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 0.5 | 14/11/2009 | 14/11/2009 |  | 2
NA | White Paper | 5 | 2009-11-15 | 2009-11-21 | [6 empty] | 1
[5 empty] | Preparation of While paper abstract and review | Yes | 1 | 17/11/2009 | 17/11/2009
[5 empty] | Study of the identified topics for white paper | Yes | 1 | 18/11/2009 | 18/11/2009 |  | 0.5
[5 empty] | Preparation White paper abstract | Yes | 1 | 19/11/2009 | 19/11/2009 |  | 0.5
[5 empty] | Final review of the White paper | Yes | 1 | 20/11/2009 | 20/11/2009 |  | 0.5
[5 empty] | Presentation of KRCF team | Yes | 1 | 21/11/2009 | 21/11/2009 |  | 0.5
1
Note on D4: ganesh: Overall Days for this phase
Note on E4: ganesh: Start date of this phase
Note on F4: ganesh: End Date of this phase

## DBMS_PRJ3_GRMTST
Waterfall Process Model Mapping | Project Execution Phase | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Activities | Applicable (Yes/No) | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Wipro Engineers Effort (PHRS) | Wipro Engineers Effort (Pdays)
Project Initiation and Planning | Project Preparedness Workshop (ppw) | 15 | 2009-06-22 | 2009-06-30
Finalization & White paper generation of project titles
Briefing of project titles
Micro Project definition
Project Team Formation
Project plan - work book preparation
Kick-off Meeting for individual projects
Requirement Analysis | Requirement Gathering and Prototyping | 9 | 2009-07-08 | 2009-07-21
[5 empty] | LAM - Requirement Analysis | Yes | 1 | 2009-08-07 | 2009-08-07 |  | 0.5
[5 empty] | Identification of Requirement Gathering Technique | No | Will be done in Func requirement phase
[5 empty] | Identification of Functional and Non Functional Requirements | Yes | 2 | 2009-08-07 | 2009-09-07 |  | 1
[5 empty] | Identification of Performance Requirements of System | No | Performance requirement is not applicable to dbms projects
[5 empty] | Inputs and Outputs to system | Yes | 1 | 2009-10-07 | 2009-10-07 |  | 1
[5 empty] | User Interface (if any) and Data Requirements | Yes | 0.5 | 13/7/2009 | 13/7/2009 |  | 0.5
[5 empty] | Internal External Interface Identification | Yes | 0.5 | 13/7/2009 | 13/7/2009 |  | 0.5
[5 empty] | Environmental Constraints | No | Environmental Constraints not applicable
[5 empty] | Requirement Related to Safety, security, and reliability aspects | No | Requirement Related to Safety, security, and reliability aspects not applicable
[5 empty] | Saturatory and Regulatory Requirements (If any) | NA | 3 | 14/7/2009 | 16/7/2009 |  | 1.5
[5 empty] | System/Business Use case generation | Yes
[5 empty] | Identification and prioritization of requirements | yes
[5 empty] | Assigning Unique ID to each requirement | yes
[5 empty] | Preparation of Requirement Specification | Yes
[5 empty] | Preparation of Requirement Traceability Sheet | Yes
[5 empty] | Requirements Review | Yes | 1 | 17/07/2009 | 17/07/2009 |  | 0.5
[5 empty] | Bugzilla - Review defect update | Yes | 2 | 18/07/09 | 21/8/2009 |  | 1
[5 empty] | Review comment analysis with team | Yes
[5 empty] | Prototyping Critical Requirements | Yes
[5 empty] | Configuration Audit | Yes
[5 empty] | KRCF - Engineers Performance Appraisal | Yes
[5 empty] | Release - Requirement Analysis Phase | yes
Architecture and Design | Design | 23 | 2009-07-22 | 2009-08-21 | [6 empty] | 1
[5 empty] | LAM - Architecture and Design | Yes | 1 | 22/7/2009 | 22/7/3009
[5 empty] | Prepare Overall Architecture, Design Pattern | Yes | 5 | 23/7/2009 | 29/7/2009 |  | 2
[5 empty] | Modular Breakdown and interface diagram | Yes | 3 | 30/7/2009 | 2009-04-08 |  | 1
[5 empty] | Identification and selection of appropriate design Methodologies (e.g. structure module, OOD, Design patterns etc.) | yes | 1 | 2009-05-08 | 2009-05-08 |  | 1
[5 empty] | Design Alternative consideration | n
[5 empty] | High Level Design (HLD) - Preparation | Yes | 3 | 7/8/2009 | 11/8/2009 |  | 1
[5 empty] | Critical Data structures | Yes | 1 | 12/8/09 | 2009-12-08 |  | 1
[5 empty] | HLD Review | Yes | 0.5 | 13/8/09 | 13/8/09 |  | 1
[5 empty] | Bugzilla - Review Defect update (HLD) | Yes | 0.5 | 13/8/09 | 13/8/09 |  | 0.5
[5 empty] | Low Level Design (LLD) Pseudo code development | Yes | 2 | 14/8/09 | 18/08/09 |  | 1
[5 empty] | LLD Review | Yes | 1 | 19/08/2009 | 19/08/2009 |  | 2
[5 empty] | Bugzilla - Review Defect update (LLD) | yes | 0.5 | 19/8/2009 | 19/8/2009 |  | 1
[5 empty] | SCM set-up for build version and release | Yes | 2 | 21/08/2009 |  |  | 1
[5 empty] | Test Design and test cases generation | Yes
[5 empty] | Update Bi-directional Traceability | Yes
[5 empty] | Review Comment Analysis with team | Yes
[5 empty] | Configuration Audit | Yes
[5 empty] | KRCF - Engineers Performance Appraisal | Yes
[5 empty] | Release - Architecture and Design | Yes
CUT/Implementation | Coding, Reviews and Unit Testing | 38 | 25/08/2009 | 16-10-2009
[5 empty] | LAM - CUT /Implementation | Yes | 0.5 | 25/8/2009 | 25/08/2009
[5 empty] | Build Setup and Build procedure documentation/guidelines | Yes | 2 | 26/08/2009 | 27/08/2009 |  | 1
[5 empty] | Identification of inter module dependencies | Yes | 4 | 28/8/2009 | 2009-02-09 |  | 2
[5 empty] | Development of the code using appropriate method - structured programming, Object Oriented Programming, Design Pattern | Yes | 20 | 2009-03-09 | 30/09/2009 |  | 10
[5 empty] | Coding as per guidelines | yes | 2 | 1/10/2009 | 2009-02-10 |  | 1
[5 empty] | Static Analysis of Code using - WiproStyle/Jtest/C++ Test/Lints/Other Tools | No | Deep check is planned use and it is covered in Development phase |  |  |  | 0.5
[5 empty] | Review of Critical section of Code | yes | 2 | 5/10/2009 | 6/10/2009 |  | 1
[5 empty] | Bugzilla - Review comments update | yes | 0.5 | 6/10/2009 | 6/10/2009 |  | 2
[5 empty] | Preparation of Unit Test plan and test cases | Yes | 2 | 7/10/2009 | 2009-09-10 |  | 1
[5 empty] | Unit Testing of components using open source testing and debugging tools | Yes | 1 | 2009-12-10 | 2009-12-10 |  | 0.5
[5 empty] | Documentation and Packaging | Yes | 2 | 13/10/2009 | 14/10/2009 |  | 1
[5 empty] | Update Bidirectional Traceability Matrix | Yes | 0.5 | 15/10/2009 | 15/10/2009 |  | 0.5
[5 empty] | Configuration Audit | Yes | 0.5 | 15/10/2009 | 15/10/2009 |  | 0.5
[5 empty] | Review comment analysis with team | Yes | 0.5 | 16/10/2009 | 16/10/2009 |  | 0.5
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 0.5 | 16/10/2009 | 16/10/2009 |  | 0.5
[5 empty] | Release - Cut/Implementation | Yes | 0.5 | 16/10/2009 | 16/10/2009 |  | 0.5
System Integration and Testing | Integration and System Testing | 20 | 2009-10-20 | 2009-11-13 | [6 empty] | 0.5
[5 empty] | LAM - System testing and Testing | Yes | 0.5 | 20/10/2009 | 20/10/2009
[5 empty] | Prepare System Test plan and test cases | Yes | 4 | 20/10/2009 | 23/10/2009 |  | 0.5
[5 empty] | Modular testing | No |  |  |  |  | 1
[5 empty] | Modular interface integration | No
[5 empty] | Build and Release | Yes | 2 | 26/10/2009 | 27/10/2009 |  | 1
[5 empty] | Configuration Audit | Yes | 1 | 28/10/2009 | 28/10/2009 |  | 0.5
[5 empty] | System testing: Execution of test cases as per test plan in 2 cycles with bug fixing | Yes | 8 | 29/10/2009 | 9/11/2009 |  | 4
[5 empty] | Perform testing for - Functional testing, Performance testing , Reliability testing, Usability Testing, Load Testing, Volume and Stress Testing | No | Not applicable for DBMS projects. |  |  |  | 10
[5 empty] | Update test result and Traceability sheet | Yes | 1 | 10/11/200 | 10/11/2009 |  | 0.5
[5 empty] | Test Result Analysis with Team | Yes | 1 | 11/11/2009 | 11/11/2009 |  | 0.5
[5 empty] | Project Presentation to KRCF & Wipro | Yes | 2 | 12/11/2009 | 13/11/2009 |  | 0.5
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 0.5 | 13/11/2009 | 13/11/2009 |  | 2
NA | White Paper | 5 | 2009-11-15 | 2009-11-21 | [6 empty] | 1
[5 empty] | Preparation of While paper abstract and review | Yes | 1 | 17/11/2009 | 17/11/2009
[5 empty] | Study of the identified topics for white paper | Yes | 1 | 18/11/2009 | 18/11/2009 |  | 0.5
[5 empty] | Preparation White paper abstract | Yes | 1 | 19/11/2009 | 19/11/2009 |  | 0.5
[5 empty] | Final review of the White paper | Yes | 1 | 20/11/2009 | 20/11/2009 |  | 0.5
[5 empty] | Presentation of KRCF team | Yes | 1 | 21/11/2009 | 21/11/2009 |  | 0.5
1
Note on D4: ganesh: Overall Days for this phase
Note on E4: ganesh: Start date of this phase
Note on F4: ganesh: End Date of this phase

## CloudComputing
Waterfall Process Model Mapping | Project Execution Phase | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Activities | Applicable (Yes/No) | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Wipro Engineers Effort (PHRS) | Wipro Engineers Effort (Pdays)
Project Initiation and Planning | Project Preparedness Workshop (ppw) | 16 | 2009-06-25 | 2009-07-16
[5 empty] | Finalization & White paper generation of project titles | Yes | 1 |  |  |  | 1
[5 empty] | Briefing of project titles | Yes | 1 |  |  |  | 1
[5 empty] | Language and Domain Training | Yes | 7 |  |  |  | 7
[5 empty] | Micro Project definition | Yes | 3 |  |  |  | 3
[5 empty] | Project Team Formation | Yes | 1 |  |  |  | 1
[5 empty] | Project plan - work book preparation | Yes | 2 |  |  |  | 3
[5 empty] | Kick-off Meeting for individual projects | Yes | 1 |  |  |  | 1
Requirement Analysis | Requirement Gathering and Prototyping | 16 | 2009-07-17 | 2009-08-07
[5 empty] | LAM - Requirement Analysis | Yes | 1 |  |  |  | 1
[5 empty] | Identification of Requirement Gathering Technique | Yes | 1 |  |  |  | 2
[5 empty] | Identification of Functional and Non Functional Requirements | Yes | 1 |  |  |  | 2
[5 empty] | Identification of Performance Requirements of System | Yes | 1 |  |  |  | 2
[5 empty] | Inputs and Outputs to system | Yes | 1 |  |  |  | 2
[5 empty] | User Interface (if any) and Data Requirements | Yes | 1 |  |  |  | 2
[5 empty] | Internal External Interface Identification | Yes | 1 |  |  |  | 2
[5 empty] | Environmental Constraints | Yes | 1 |  |  |  | 2
[5 empty] | Requirement Related to Safety, security, and reliability aspects | Yes | 1 |  |  |  | 2
[5 empty] | Saturatory and Regulatory Requirements (If any) | NA
[5 empty] | System/Business Use case generation | Yes | 1 |  |  |  | 2
[5 empty] | Identification and prioritization of requirements | Yes | 1 |  |  |  | 2
[5 empty] | Assigning Unique ID to each requirement | NA
[5 empty] | Preparation of Requirement Specification | Yes | 1 |  |  |  | 2
[5 empty] | Preparation of Requirement Traceability Sheet | NA
[5 empty] | Requirements Review | Yes | 1 |  |  |  | 2
[5 empty] | Bugzilla - Review defect update | Yes | 1 |  |  |  | 2
[5 empty] | Review comment analysis with team | Yes | 0.5 |  |  |  | 1
[5 empty] | Prototyping Critical Requirements | Yes | 1 |  |  |  | 3
[5 empty] | Configuration Audit | Yes | 0.5 |  |  |  | 1
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 0.5 |  |  |  | 1
[5 empty] | Release - Requirement Analysis Phase | Yes | 0.5 |  |  |  | 1
Architecture and Design | Design | 20 | 2009-08-10 | 2009-09-07
[5 empty] | LAM - Architecture and Design | Yes | 1 |  |  |  | 1
[5 empty] | Prepare Overall Architecture, Design Pattern | Yes | 2 |  |  |  | 4
[5 empty] | Modular Breakdown and interface diagram | Yes | 1 |  |  |  | 2
[5 empty] | Identification and selection of appropriate design Methodologies (e.g. structure module, OOD, Design patterns etc.) | Yes | 2 |  |  |  | 5
[5 empty] | Design Alternative consideration | Yes | 2 |  |  |  | 3
[5 empty] | High Level Design (HLD) - Preparation | Yes | 1 |  |  |  | 3
[5 empty] | Critical Data structures | Yes | 1 |  |  |  | 2
[5 empty] | HLD Review | Yes | 0.5 |  |  |  | 1
[5 empty] | Bugzilla - Review Defect update (HLD) | Yes | 0.5 |  |  |  | 1
[5 empty] | Low Level Design (LLD) Pseudo code development | Yes | 2 |  |  |  | 4
[5 empty] | LLD Review | Yes | 0.5 |  |  |  | 1
[5 empty] | Bugzilla - Review Defect update (LLD) | Yes | 0.5 |  |  |  | 1
[5 empty] | SCM set-up for build version and release | Yes | 1 |  |  |  | 2
[5 empty] | Test Design and test cases generation | Yes | 1 |  |  |  | 2
[5 empty] | Update Bi-directional Traceability | NA
[5 empty] | Review Comment Analysis with team | Yes | 1 |  |  |  | 2
[5 empty] | Configuration Audit | Yes | 1 |  |  |  | 2
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 1 |  |  |  | 2
[5 empty] | Release - Architecture and Design | Yes | 1 |  |  |  | 2
CUT/Implementation | Coding, Reviews and Unit Testing | 24 | 2009-09-08 | 2009-10-09
[5 empty] | LAM - CUT /Implementation | Yes | 1 |  |  |  | 1
[5 empty] | Build Setup and Build procedure documentation/guidelines | Yes | 1 |  |  |  | 1
[5 empty] | Identification of inter module dependencies | Yes | 2 |  |  |  | 3
[5 empty] | Development of the code using appropriate method - structured programming, Object Oriented Programming, Design Pattern | Yes | 4 |  |  |  | 8
[5 empty] | Coding as per guidelines | Yes | 1 |  |  |  | 2
[5 empty] | Static Analysis of Code using - WiproStyle/Jtest/C++ Test/Lints/Other Tools | Yes | 2 |  |  |  | 3
[5 empty] | Review of Critical section of Code | Yes | 2 |  |  |  | 3
[5 empty] | Bugzilla - Review comments update | Yes | 1 |  |  |  | 2
[5 empty] | Preparation of Unit Test plan and test cases | Yes | 3 |  |  |  | 2
[5 empty] | Unit Testing of components using open source testing and debugging tools | Yes | 1 |  |  |  | 3
[5 empty] | Documentation and Packaging | Yes | 1 |  |  |  | 2
[5 empty] | Update Bidirectional Traceability Matrix | NA
[5 empty] | Configuration Audit | Yes | 1 |  |  |  | 1
[5 empty] | Review comment analysis with team | Yes | 2 |  |  |  | 2
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 1 |  |  |  | 1
[5 empty] | Release - Cut/Implementation | Yes | 1 |  |  |  | 1
System Integration and Testing | Integration and System Testing | 25 | 2009-10-12 | 2009-11-13
[5 empty] | LAM - System testing and Testing | Yes | 1 |  |  |  | 1
[5 empty] | Prepare System Test plan and test cases | Yes | 2 |  |  |  | 4
[5 empty] | Modular testing | Yes | 2 |  |  |  | 3
[5 empty] | Modular interface integration | Yes | 2 |  |  |  | 4
[5 empty] | Build and Release | Yes | 2 |  |  |  | 2
[5 empty] | Configuration Audit | Yes | 1 |  |  |  | 1
[5 empty] | System testing: Execution of test cases as per test plan in 2 cycles with bug fixing | Yes | 4 |  |  |  | 8
[5 empty] | Perform testing for - Functional testing, Performance testing , Reliability testing, Usability Testing, Load Testing, Volume and Stress Testing | Yes | 5 |  |  |  | 8
[5 empty] | Update test result and Traceability sheet | Yes | 1 |  |  |  | 2
[5 empty] | Test Result Analysis with Team | Yes | 2 |  |  |  | 2
[5 empty] | Project Presentation to KRCF & Wipro | Yes | 2 |  |  |  | 2
[5 empty] | KRCF - Engineers Performance Appraisal | Yes | 1 |  |  |  | 1
NA | White Paper | 10 | 2009-08-25 | 2009-09-08
[5 empty] | Preparation of While paper abstract and review | Yes
[5 empty] | Study of the identified topics for white paper | Yes
[5 empty] | Preparation White paper abstract | Yes
[5 empty] | Final review of the White paper | Yes
[5 empty] | Presentation of KRCF team | Yes
| Buffer Time | 12 Days | 2009-11-16 | 2009-12-02
Note on D4: ganesh: Overall Days for this phase
Note on E4: ganesh: Start date of this phase
Note on F4: ganesh: End Date of this phase

## HPC
Waterfall Process Model Mapping | Project Execution Phase | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Activities | Applicable (Yes/No) | Duration (Days) | Start Date (DD-MON-YY) | End Date (DD-MON-YY) | Wipro Engineers Effort (PHRS) | Wipro Engineers Effort (Pdays)
Project Initiation and Planning | Project Preparedness Workshop (ppw)
Finalization & White paper generation of project titles
Briefing of project titles
Micro Project definition
Project Team Formation
Project plan - work book preparation
Kick-off Meeting for individual projects
Requirement Analysis | Requirement Gathering and Prototyping | 20 | 2009-07-08 | 2009-08-04
LAM - Requirement Analysis
Identification of Requirement Gathering Technique
Identification of Functional and Non Functional Requirements
Identification of Performance Requirements of System
Inputs and Outputs to system
User Interface (if any) and Data Requirements
Internal External Interface Identification
Environmental Constraints
Requirement Related to Safety, security, and reliability aspects
Saturatory and Regulatory Requirements (If any)
System/Business Use case generation
Identification and prioritization of requirements
Assigning Unique ID to each requirement
Preparation of Requirement Specification
Preparation of Requirement Traceability Sheet
Requirements Review
Bugzilla - Review defect update
Review comment analysis with team
Prototyping Critical Requirements
Configuration Audit
KRCF - Engineers Performance Appraisal
Release - Requirement Analysis Phase
Architecture and Design | Design | 20 | 2009-08-05 | 2009-09-01
LAM - Architecture and Design
Prepare Overall Architecture, Design Pattern
Modular Breakdown and interface diagram
Identification and selection of appropriate design Methodologies (e.g. structure module, OOD, Design patterns etc.)
Design Alternative consideration
High Level Design (HLD) - Preparation
Critical Data structures
HLD Review
Bugzilla - Review Defect update (HLD)
Low Level Design (LLD) Pseudo code development
LLD Review
Bugzilla - Review Defect update (LLD)
SCM set-up for build version and release
Test Design and test cases generation
Update Bi-directional Traceability
Review Comment Analysis with team
Configuration Audit
KRCF - Engineers Performance Appraisal
Release - Architecture and Design
CUT/Implementation | Coding, Reviews and Unit Testing | 49 | 2009-09-02 | 2009-11-09
LAM - CUT /Implementation
Build Setup and Build procedure documentation/guidelines
Identification of inter module dependencies
Development of the code using appropriate method - structured programming, Object Oriented Programming, Design Pattern
Coding as per guidelines
Static Analysis of Code using - WiproStyle/Jtest/C++ Test/Lints/Other Tools
Review of Critical section of Code
Bugzilla - Review comments update
Preparation of Unit Test plan and test cases
Unit Testing of components using open source testing and debugging tools
Documentation and Packaging
Update Bidirectional Traceability Matrix
Configuration Audit
Review comment analysis with team
KRCF - Engineers Performance Appraisal
Release - Cut/Implementation
System Integration and Testing | Integration and System Testing | 14 | 2009-11-10 | 2009-11-20
LAM - System testing and Testing
Prepare System Test plan and test cases
Modular testing
Modular interface integration
Build and Release
Configuration Audit
System testing: Execution of test cases as per test plan in 2 cycles with bug fixing
Perform testing for - Functional testing, Performance testing , Reliability testing, Usability Testing, Load Testing, Volume and Stress Testing
Update test result and Traceability sheet
Test Result Analysis with Team
Project Presentation to KRCF & Wipro
KRCF - Engineers Performance Appraisal
NA | White Paper | 10 | 2009-09-10 | 2009-10-15
Preparation of While paper abstract and review
Study of the identified topics for white paper
Preparation White paper abstract
Final review of the White paper
Presentation of KRCF team
Note on D4: ganesh: Overall Days for this phase
Note on E4: ganesh: Start date of this phase
Note on F4: ganesh: End Date of this phase